## Loop Tasks
Tasks List | Status | Resource Name | Date
Remove unsused tables from MYSQL | Not started | Naveen Adusumilli | 08/29/2024
Remove unused collection from Mongo DB | Not started | Naveen Adusumilli | 08/29/2024
Remove unused collection from Mongo DB | Not started | Venkat | 08/29/2024
Isolate Pulse Demo Backend, remove accesses | Not started | Gopalswamy Ramalingam | 08/23/2024
Add alerts data in Pulse Demo | Not started | Ajay kumar | 08/23/2024
Forms flow Integration Backend | Not started | Gopalswamy Ramalingam | 08/23/2024
Form Flow Integration UI | Not started | Mahesh Katti | 08/23/2024
Discussing Bots restart | Not started | Sai Sampath Chinthavatla | 08/23/2024
Discussing Bots restart | Not started | Kishore Aerravelly | 08/23/2024
Discussing Bots restart | Not started | Venkat | 08/23/2024
Discussing Bots restart | Not started | Achyut Deshpande | 08/23/2024
Verify collections of Mongo DB dev, QA, Prod | Not started | Shrashti Singhal | 08/23/2024
Automate / schedule restarting of bots Prime and AVH- weekly, 4 days whichever is the relevant time period | Not started | Achyut Deshpande | 08/22/2024
Automate / schedule restarting of bots Prime and AVH- weekly, 4 days whichever is the relevant time period | Not started | Sai Sampath Chinthavatla | 08/22/2024
Find Social Handles for AVMC | Not started | Sneha Guthe | 08/21/2024
Find Social Handles for New Health | Not started | Sneha Guthe | 08/21/2024
Deploy alerts using filebeat( stop sys log) | Not started | Achyut Deshpande | 08/21/2024
Deploy alerts using filebeat( stop sys log) | Not started | Sai Sampath Chinthavatla | 08/21/2024
Swimlane turbulane | Not started | Gopalswamy Ramalingam | 08/21/2024
Write test cases for the sprint | Not started | Sneha Guthe | 08/21/2024
Repeated IOC Values confirmation for different Threat Actors | Not started | Venkat | 08/20/2024
Upgrade suricata on all sensors | Not started | Achyut Deshpande | 08/20/2024
Upgrade suricata on all sensors | Not started | Sai Sampath Chinthavatla | 08/20/2024
Darkeye Mongo Db Upgrade further | Not started | Gopalswamy Ramalingam | 08/20/2024
Remove 1M alerts from AVH | Not started | Naveen Adusumilli | 08/20/2024
Follow up on corrupted MYSQL server | Not started | Gopalswamy Ramalingam | 08/20/2024
Follow up on corrupted MYSQL server | Not started | Achyut Deshpande | 08/20/2024
Run counter table deletion Code on AVH- Pending because of hexadecimal values | Not started | Naveen Adusumilli | 08/20/2024
Run counter table deletion Code on AVH- Pending because of hexadecimal values | Not started | Achyut Deshpande | 08/20/2024
Follow up with Nagraj on Static IPS for datacenters | Not started | Achyut Deshpande | 08/20/2024
Graffana Alerts on Prime Pulse Environment RnD | Not started | Gopalswamy Ramalingam | 08/20/2024
Follow up with Daniel on not able to access few sensors | Not started | Achyut Deshpande | 08/20/2024
Write code to delete Snort alerts- per day | Not started | Varad Bhalsing | 08/20/2024
Research on Alerting on resources Threshold for Pulse | Not started | Gopalswamy Ramalingam | 08/20/2024
SQL table matching across all environments | Done | Varad Bhalsing | 08/23/2024
Mongo DB Collections mapping across all environments | Done | Varad Bhalsing | 08/23/2024
Add users to the new org Darkeye | Done | Sneha Guthe | 08/23/2024
Verify the groupings of Database tables given by Somesh | Done | Somesh | 08/22/2024
Create new organization in Darkeye | Done | Naveen Adusumilli | 08/22/2024
Have I been pawned check on support email | Done | Venkat | 08/22/2024
Offline Swimlane deployment- Testing Pending by Thota | Done | Venkat | 08/22/2024
Re-Deploy forms flow AI 2 modules | Done | Gopalswamy Ramalingam | 08/21/2024
Migration of AI services on dev, qa, and prod for Night hawk | Done | Gopalswamy Ramalingam | 08/21/2024
Follow up with Davos about the SSL certificate | Done | Achyut Deshpande | 08/21/2024
Follow up on corrupted MYSQL server | Not started | Achyut Deshpande | 08/06/2024
Follow up on corrupted MYSQL server | Not started | Gopalswamy Ramalingam | 08/06/2024
Set up sentry in Production Darkeye | Not started | Ajay kumar | 08/06/2024
Set up sentry in Production Darkeye | Not started | Naveen Adusumilli | 08/06/2024
Set up sentry in Production Darkeye | Not started | SaradhiMuneendra Gundabattina | 08/06/2024
Run counter table deletion Code on AVH- Pending because of hexadecimal values | Not started | Achyut Deshpande | 08/06/2024
Run counter table deletion Code on AVH- Pending because of hexadecimal values | Not started | Naveen Adusumilli | 08/06/2024
Follow up with Daniel on not able to access few sensors | Not started | Achyut Deshpande | 08/06/2024
Remove 1M alerts from AVH | Not started | Naveen Adusumilli | 08/06/2024
Write code to delete Snort alerts- per day | Not started | Varad Bhalsing | 08/06/2024
Upgrade suricata on all sensors | Not started | Achyut Deshpande | 08/06/2024
Upgrade suricata on all sensors | Not started | Sai Sampath Chinthavatla | 08/06/2024
Graffana Alerts on Prime Pulse Environment RnD | Not started | Gopalswamy Ramalingam | 08/06/2024
Research on Alerting on resources Threshold for Pulse | Not started | Gopalswamy Ramalingam | 08/06/2024
Darkeye Mongo Db Upgrade further | Not started | Gopalswamy Ramalingam | 08/06/2024
Offline Swimlane deployment- Testing Pending by Thota | Not started | Venkat | 08/06/2024
Follow up with Nagraj on Static IPS for datacenters | Not started | Achyut Deshpande | 08/06/2024
Cassandra Events table vs Counter tables | Not started | Shrashti Singhal | 08/06/2024
Cassandra Snort dump in new instance to help Varad test snort table deletion code | Done | Gopalswamy Ramalingam | 08/14/2024
Cassandra Snort dump in new instance to help Varad test snort table deletion code | Done | Achyut Deshpande | 08/14/2024
Identify Sensor for IDS | Done | Venkat | 08/13/2024
Task list for setting up Kubernetes on Prime servers | Done | Gopalswamy Ramalingam | 08/13/2024
Reply to Davos about the SSL certificate | Done | Achyut Deshpande | 08/06/2024

## Sprint Tasks
Summary | Assignee | Reporter | Status | Created
Content | Pranav Ramchandra Sarda | Shrashti Singhal | Done | 2024-08-23 03:38
Design | Ritika | Shrashti Singhal | Done | 2024-08-23 03:38
Design | Ritika | Shrashti Singhal | Done | 2024-08-23 03:36
Inserting data in DB directly | Shrashti Singhal | Shrashti Singhal | Done | 2024-08-23 03:35
Creation of new columns in DB(from services) | Amitabh Sharma | Shrashti Singhal | Done | 2024-08-23 03:34
Data for registration Date | Varad Balasaheb Bhalsing | Shrashti Singhal | Done | 2024-08-23 03:32
Data for registrar for all domains(whois) | Varad Balasaheb Bhalsing | Shrashti Singhal | Done | 2024-08-23 03:32
Change of Services for UI | Amitabh Sharma | Shrashti Singhal | Done | 2024-08-23 03:31
UI Development | Mahesh Katti | Shrashti Singhal | Done | 2024-08-23 03:30
Standardizing Domain squatting in Self Assessment & vendor Assessment | Mahesh Katti | Shrashti Singhal | Done | 2024-08-23 03:29
Download Users from User Management | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-20 04:38
Integration | Mahesh Katti | Shrashti Singhal | Done | 2024-08-20 03:22
UI development | Mahesh Katti | Shrashti Singhal | Done | 2024-08-20 03:22
Java Services | Rishav | Shrashti Singhal | Done | 2024-08-20 03:22
Design | Ritika | Shrashti Singhal | Done | 2024-08-20 03:22
Created Date/ Date of Registration | Varad Balasaheb Bhalsing | Shrashti Singhal | Not Required/Duplicate | 2024-08-20 01:08
Scan date | Amitabh Sharma | Shrashti Singhal | Not Required/Duplicate | 2024-08-20 01:08
Registration date - date format standardization, domain squatting | Varad Balasaheb Bhalsing | Shrashti Singhal | Not Required/Duplicate | 2024-08-19 04:27
Exception Handling of Login in case of Invalid user- Sentry Issue | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-19 03:15
Exception Handling of Scan Manager- Sentry Issue | Ajay Kumar Devarakonda | Shrashti Singhal | Not Required/Duplicate | 2024-08-19 03:14
Threat Prism - Export - Tags Data is missing (PROD Issue). | Mahesh Katti | Sneha Sonyabapu Guthe | Done | 2024-08-19 01:53
Dev Darkeye Login email sends url for prod- needs correction in email template | Naveen Adusumilli | Shrashti Singhal | Done | 2024-08-19 01:26
Threats - DNS | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 05:52
Threats - Websites | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 05:52
Threats - Assets Inventory | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 05:51
SSL List | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 05:09
SOA Configuration Check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:52
NS Configuration Check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:52
MX Configuration Check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:52
Real-Time Blackhole Check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:51
Mail Servers Response | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:51
Name Servers Respond | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:50
Mail Server Reverse IP Addresses Match | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 04:49
Miscellaneous Vulnerabilities | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 01:42
Web Analysis - Config Check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 01:13
Web Analysis - Pages Parsed | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 01:00
WHOIS & DNS Name servers match | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 00:56
Domain Check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 00:55
Assets config check | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 00:38
Open cloud storage | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 00:37
Open ports & services | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | Done | 2024-08-14 00:35
Deployment Changes | gopal | Shrashti Singhal | Done | 2024-08-13 02:08
UI Changes | Mahesh Katti | Shrashti Singhal | Done | 2024-08-13 02:08
Design for archiving and performing other actions | Ritika | Shrashti Singhal | Done | 2024-08-13 02:06
UI Changes | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-13 01:47
Service enhancing | Naveen Adusumilli | Shrashti Singhal | Done | 2024-08-13 01:46
Need to design view for child node( for more number of nodes) | Ritika | Shrashti Singhal | Done | 2024-08-13 01:46
Design for Indicating that the chart is clickable | Ritika | Shrashti Singhal | Done | 2024-08-13 01:43
Breaches- Github Secrets | Mahesh Katti | Shrashti Singhal | Done | 2024-08-13 01:38
Spelling correction of Registrar | Mahesh Katti | Shrashti Singhal | Done | 2024-08-12 06:48
Redirecting source to a website- ThreatPrism | Mahesh Katti | Shrashti Singhal | Done | 2024-08-12 04:57
Change of services | Karan Pandey | Shrashti Singhal | Done | 2024-08-12 04:34
DB Change for self Assessment | Shrashti Singhal | Shrashti Singhal | Done | 2024-08-12 04:34
Add mimecast tag in UI - self Assessment | Mahesh Katti | Shrashti Singhal | Done | 2024-08-12 04:34
return a tag after entering domain to mimecast | Varad Balasaheb Bhalsing | Shrashti Singhal | Done | 2024-08-12 04:33
Services for achieving user | Karan Pandey | Shrashti Singhal | Done | 2024-08-12 04:28
UI changes | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-12 04:28
Archive User in DB | Ajay Kumar Devarakonda | Shrashti Singhal | Done | 2024-08-12 04:27
Highlighting on Hovering on ThreatPrism | Mahesh Katti | Shrashti Singhal | Done | 2024-08-12 04:23
Service change is required | Rishav | Shrashti Singhal | Done | 2024-08-12 04:10
If registrar name is not returned by API, let user fill it | Mahesh Katti | Shrashti Singhal | Done | 2024-08-12 04:10
UI integration | Mahesh Katti | Shrashti Singhal | Done | 2024-08-12 04:10
Run Whois here on domain name to fetch registrar automatically | Varad Balasaheb Bhalsing | Shrashti Singhal | Done | 2024-08-12 04:09
Search on Domain Squatting for Self-Assessment. | Amitabh Sharma | Sneha Sonyabapu Guthe | Done | 2024-08-09 04:48
Allein Vault OTX Updater | Ajay Kumar Devarakonda | Shrashti Singhal | Done | 2024-08-08 22:48
Malpedia Updater | Ajay Kumar Devarakonda | Shrashti Singhal | Done | 2024-08-08 22:47
NAICS- one service for NAICS(place in prod env), use dev, qa, and prod Dbs accordingly | Somesh Fengade | Shrashti Singhal | Not Required/Duplicate | 2024-08-08 05:08
nighthawk- one service for (place in prod env)prod, but individual DB management for dev, qa, prod | Somesh Fengade | Shrashti Singhal | Has Blocker | 2024-08-08 05:07
darkWatch- one service (place in prod env)prod, but individual DB management for dev, qa, prod | Somesh Fengade | Shrashti Singhal | Done | 2024-08-08 05:06
AI Services Management - Darkwatch | Somesh Fengade | Shrashti Singhal | Done | 2024-08-08 05:05
Archive User | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-08 04:30
Sidebar collapse feature on all tabs | Mahesh Katti | Shrashti Singhal | Done | 2024-08-08 04:27
Add button should be diabled | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-08 04:20
Fill registrar yourself | Mahesh Katti | Shrashti Singhal | Done | 2024-08-08 04:18
Domain Squatting for self assessment- add mimecast tag | Mahesh Katti | Shrashti Singhal | Done | 2024-08-07 06:47
Attack surface Visualization enhancement | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-07 03:44
CSV download for more details | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-08-06 23:44
Add new IOC types in adversaries | Mahesh Katti | Shrashti Singhal | Done | 2024-08-06 01:07
Darkeye User Manual | Pranav Ramchandra Sarda | Shrashti Singhal | Done | 2024-07-27 11:41
Updating IOC Parser Code for 2 sources | Ajay Kumar Devarakonda | Shrashti Singhal | Done | 2024-07-23 04:59
Change Google Analytics Tag for Prod | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-07-15 22:52
Filter Integration on UI | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-05-22 02:25
Java Service on Scan Status | Amitabh Sharma | Shrashti Singhal | Done | 2024-05-22 02:25
Filter integration on UI | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-05-22 02:24
Java Services for Filter | Amitabh Sharma | Shrashti Singhal | Done | 2024-05-22 02:24
UI filter enable/Integration | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-05-22 02:23
Java services for Filter on pagination | Amitabh Sharma | Shrashti Singhal | Done | 2024-05-22 02:23
Integrate the end points- if required to show In progress | SaradhiMuneendra Gundabattina | Shrashti Singhal | Done | 2024-05-22 02:16
Implement a In Progress Scan status in Services | Amitabh Sharma | Shrashti Singhal | Done | 2024-05-22 02:16
Add a third scan Status- IN PROGRESS | Ajay Kumar Devarakonda | Shrashti Singhal | Done | 2024-05-22 02:15
Progress status, when scan is in progress | Naveen Adusumilli | Shrashti Singhal | Done | 2024-05-22 01:42
Filter on Vendor Risk Rating- Vendor Assessment | Naveen Adusumilli | Shrashti Singhal | Done | 2024-05-22 01:42
Filter on Reputation Score- Vendor Assessment | Naveen Adusumilli | Shrashti Singhal | Done | 2024-05-22 01:42
Filter on Scanned Status- Vendor Assessment | Naveen Adusumilli | Shrashti Singhal | Done | 2024-05-22 01:41
Spark setup in kubernetes | gopal | Shrashti Singhal | In Progress | 2024-08-26 22:38
MYSQL | gopal | Shrashti Singhal | Done | 2024-08-22 22:49
Bots deployment | gopal | Shrashti Singhal | To Do | 2024-08-06 03:44
Clickhouse deployment | gopal | Shrashti Singhal | Done | 2024-08-06 03:43
Kafka and Zookeeper setup | gopal | Shrashti Singhal | Done | 2024-08-06 03:42
Setting up Kubernetes | gopal | Shrashti Singhal | Done | 2024-08-06 03:42
Setup Data Model on UAT | gopal | Shrashti Singhal | To Do | 2024-08-06 03:28
Most Table Jobs Cleanup | gopal | Shrashti Singhal | To Do | 2024-08-06 03:28
Protocols Bot Implementation | Kishore Aerravelly | Shrashti Singhal | In Progress | 2024-08-06 03:28
Alerts Bot Implementation | Naveen Adusumilli | Shrashti Singhal | In Progress | 2024-08-06 03:26
DNS Bot Implementation | Naveen Adusumilli | Shrashti Singhal | In Progress | 2024-08-06 03:26
Connections Bot Implementation | Naveen Adusumilli | Shrashti Singhal | In Progress | 2024-08-06 03:26
Containerization of tech Stack | Kishore Aerravelly | Shrashti Singhal | In Progress | 2024-08-06 00:29
Writing Spark Bots | Naveen Adusumilli | Shrashti Singhal | In Progress | 2024-08-06 00:29
Infrastructure for Click House | gopal | Shrashti Singhal | In Progress | 2024-08-06 00:29