## Sprint Tasks
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Updated | Sprint
Subtask | DPI-332 | 14553 | New Service integration | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-27
Task | DPI-331 | 14544 | Vendor Assessment(individual) change end date for continuous monitoring depending upon the type of CM | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-06-20
Task | DPI-330 | 14543 | Self Assessment- change end date for continuous monitoring depending upon the type of CM | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-06-20
Subtask | DPI-323 | 14536 | Services Optimization | Manoj Singh Rawat | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-19
Subtask | DPI-322 | 14535 | Code optimization | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-19
Task | DPI-321 | 14534 | Performance Enhancement- SentiMind(Page Hangs) | Shrashti Singhal | 60ba18cb66df7900708f9114 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-06-19
Bug | DPI-320 | 14533 | Data count mismatch in many tools | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-06-19
Task | DPI-319 | 14528 | Data mismatch between Darkeye assessment and reports | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done- to be pushed on Dev | 2024-06-07
Bug | DPI-312 | 14517 | Sentiment Distribution – Arrange the UI alignment | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-06-03
Subtask | DPI-299 | 14490 | user Keyclock configuration- enabling and disabling | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-24
Subtask | DPI-298 | 14489 | Add a support email address in cc | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-24
Subtask | DPI-297 | 14488 | Need to address Key clock refresh token | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Ready to Move To PROD | 2024-05-24
Subtask | DPI-289 | 14463 | Integration of UI and Services | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Subtask | DPI-288 | 14462 | Change Java Service | Manoj Singh Rawat | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Subtask | DPI-287 | 14461 | Create UI | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Subtask | DPI-286 | 14460 | UI Service Integration | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Subtask | DPI-285 | 14459 | Change Java Service and Mongo DB Query | Manoj Singh Rawat | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Subtask | DPI-284 | 14458 | Create Ui | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Task | DPI-283 | 14457 | SentiMind- Posts on Individual Social Media New Design | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Task | DPI-282 | 14456 | SentiMind- Comments on Individual Social Media New Design | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Subtask | DPI-262 | 14436 | Integration with UI- Notification Bell | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-261 | 14435 | Notify the user on 59th Days, who onboarded the Vendor POC by notification Email | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-260 | 14434 | Notify the user on 59th Days, who onboarded the Vendor POC by notification Bell | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Task | DPI-259 | 14433 | Vendor POC User Archive Notification | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Subtask | DPI-257 | 14431 | Disabling/ Archiving the POC from UI after 60 days | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | In Progress | 2024-05-22
Subtask | DPI-256 | 14430 | Timer of 60 days when Vendor POC is onboarded | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-255 | 14429 | Set flags at user onboarding Onboarded, Inactive, Not Onboarded | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-249 | 14423 | Replace report icon in UI | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Ready to Move To PROD | 2024-05-22
Subtask | DPI-248 | 14422 | Provide a new Icon for report | Ritika | 712020:2d9accdf-0317-4bb6-bb87-b5fb4b160527 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Ready to Move To PROD | 2024-05-22
Subtask | DPI-241 | 14415 | Show the email Id to user | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-240 | 14414 | Java service to fetch Email ID | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-239 | 14413 | Take down domain uses WHOIS, if not please enable to fetch abuse email id to report | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-22
Subtask | DPI-238 | 14412 | Changing of IP from another | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Ready to Move To PROD | 2024-05-22
Subtask | DPI-237 | 14411 | Session Time out | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Ready to Move To PROD | 2024-05-22
Task | DPI-233 | 14407 | Lifetime Management of Vendors POC | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Task | DPI-232 | 14406 | Take Down Domain- Reporting email ID isn't avaiable | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done- to be pushed on Dev | 2024-05-22
Task | DPI-231 | 14405 | Session Management | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22
Task | DPI-226 | 14400 | Vendor Assessment- change end date for continuous monitoring depending upon the type of CM | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-21
Task | DPI-221 | 14394 | Report Icon is Settings- New icon | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-10
Subtask | PPI-130 | 14556 | Cron job to schedule | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-27
Subtask | PPI-129 | 14555 | Add rules to MYSQL | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-27
Subtask | PPI-128 | 14554 | script that gets all the new rules | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-27
Task | PPI-127 | 14552 | Payload and Rules missing in Suricata Alerts | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-06-26
Story | PPI-126 | 14551 | Alerts for auto deletion of Cassandra DOD tables | C Sai Sampath | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Story | PPI-125 | 14550 | Alerts for Auto deletion of Spark Logs | C Sai Sampath | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Story | PPI-124 | 14549 | Server Storage alerts on Prime | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Story | PPI-123 | 14548 | Server Storage Alerts on AVH | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Story | PPI-122 | 14547 | File Beat Generator Utility to create consistent yamls | Somesh Fengade | 712020:8e75e228-f554-4396-9a80-82361f5f4833 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Story | PPI-121 | 14546 | CI CD deployment of Auto Counter Tables Deletion | gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Story | PPI-120 | 14545 | Auto Deletion of Cassandra Counter Tables | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-06-26
Bug | PPI-119 | 14532 | Ask Pulse is not working in AVH | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-06-19
Bug | PPI-118 | 14531 | No revenue data on Prime( Radcharges not mounted) | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-16
Bug | PPI-117 | 14530 | Alerts Tab no data on AVH | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-16
Subtask | PPI-115 | 14527 | Create one global date filters for scan dates | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-07
Subtask | PPI-114 | 14526 | Delete local Date filters | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-07
Subtask | PPI-113 | 14525 | Provide the list of last scan dates from services | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-07
Task | PPI-112 | 14524 | Change of filters for IOE Vulnerablity | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-06-07
Task | PPI-111 | 14511 | Load Data in dev for Testing | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-108 | 14502 | Auto Deletion of Spark logs Prime | C Sai Sampath | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-107 | 14501 | Auto Deletion of Spark Logs in AVH | C Sai Sampath | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-106 | 14500 | Auto Deletion of Spark Logs in harvard | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-105 | 14499 | AVH Deployment of Pulse by Using new Pulse(unified)branch | gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-104 | 14498 | Storage Alerts on Prime Pulse | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-103 | 14497 | Storage Alerts on AVH | C Sai Sampath | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-102 | 14496 | Storage alerts on Harvard | C Sai Sampath | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-101 | 14495 | Harvard Pulse deployment | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-100 | 14494 | Auto CI CD Pulse deployment Pipeline | gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-99 | 14493 | deployment of Unified Pulse Branch to Pulse Dev | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-98 | 14492 | Single Unified Pulse Branch Creation | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-27
Task | PPI-97 | 14487 | Swimlane offline Deployment | V Thota | 5d7508ca8ce6b60c38109fd3 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23
Task | PPI-96 | 14486 | Replacement of Subnets on Filebeats- Prime | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Subtask | PPI-92 | 14481 | Message on old session that user is kicked out because of new session | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Subtask | PPI-91 | 14480 | Add a error message on loged out session | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Bug | PPI-90 | 14479 | Ask Pulse isn't working in dev | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Ready to Move PROD | 2024-05-23
Bug | PPI-89 | 14478 | Asset Inventory- Individual Devices- Change the placement of dollor sign( in front of the value) | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Bug | PPI-88 | 14477 | Asset Inventory- GRID VIEW- Add Likelihood of Loss(use the fix from Demo) | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Bug | PPI-87 | 14476 | Asset Inventory- GRID VIEW- Add risk( use the fix from Demo) | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Bug | PPI-86 | 14475 | Asset Inventory- GRID View- Online device not working(use the fix from demo)- AVH | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23
Subtask | PPI-85 | 14474 | Session management when same user switch from one IP to other | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Subtask | PPI-84 | 14473 | Add timer for inactive sessions | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Task | PPI-83 | 14472 | Session Management | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22
Task | PPI-82 | 14471 | Ask Pulse as a deployable module for devops on every new installation | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Test on PROD | 2024-05-22
Task | PPI-81 | 14470 | Auto Alerts Filter on Pulse (python Code) | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Test on PROD | 2024-05-22
Bug | PPI-60 | 14249 | Dashboard- Merge 2nd and 4th Widget | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-03-09
Bug | PPI-54 | 14197 | Risk Lens – IOE Risk – Global Filter is not resetting the Widget Data. | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-03-01
Bug | PPI-42 | 14185 | Investigation – Managed & Unmanaged Devices – View All Filter is not working properly. (In the View All We Need Data in Table View) | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-03-01
Bug | PPI-41 | 14184 | Revenue Dormant Devices – No of Device count should have to increase (Y Axis) As Graph Bar values going more than that. | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-03-01
Bug | PPI-40 | 14183 | Device Risk Comparison Widget is not working properly.- Use the fix from Demo | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Ready to Move PROD | 2024-03-01
Task | PPI-29 | 14168 | Need to Show Table View If the Records are greater than 10 under the Inbound & Outbound. | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-02-20

## Loop Tasks
Tasks List | Resource Name | Date | Status
Mount radio folder- Pulse Prime- Thota Following up with Raghu | Achyut Deshpande | 2024-06-14 | In Progress
Test the Ask Pulse module on AVH | Sneha Guthe | 2024-06-19 | To do
Configurations on server and sensors, disk space alerts on 80% Prime- Whitelisting Teams | Achyut Deshpande | 2024-05-28 | Done
Schedule Swimlane- Mimecast Script (after one time run) ON HOLD | Varad Bhalsing | 2024-06-04 | Done
Prime SQL Backup | Achyut Deshpande | 2024-06-10 | Done
Prime SQL Backup | Gopalswamy Ramalingam | 2024-06-10 | Done
Take Dev Mongo DB creds/ as backup of Naveen for whitelisting- add support@culinda.com email address | Thota | 2024-05-28 | Done
Take Dev Mongo DB creds/ as backup of Naveen for whitelisting- add support@culinda.com email address | Gopalswamy Ramalingam | 2024-05-28 | Done
Research on Alerting on resources Threshold for Pulse | Achyut Deshpande | 2024-06-14
Offline Swimlane deployment- Testing Pending by Thota | Thota | 2024-05-22 | In Review
AVH 11 devices only, Rapid 7 , need to connect with AVH, discussion with Thota on changes | Naveen Adusumilli | 2024-06-10 | Done
Delete counter tables data older than 3 months Prime | Manoj Singh | 2024-06-14
Datacenters onboard pending- VLans not visible - PENDING FROM PRIME | Sai Sampath Chinthavatla | 2024-06-14
IOE Risk in AVH - check with Uma | Shrashti Singhal | 2024-06-14
Change file beat for the facilities found incorrect in testing | Sai Sampath Chinthavatla | 2024-06-12 | In Progress
Verify Inbound Outbound data for devices- Pulse Prime( issue should resolve from 15th May, Changes wont be reflected on old dates) ON HOLD as Pulse Prime UI is inaccessible | Sneha Guthe | 2024-05-15 | On Hold
Running the script for Swimlane for ~6K prime Vendors, The script is running from 3 weeks. 1 more week to go for 1 time addition of domain squatting for Prime Vendors | Varad Bhalsing | 2024-06-03 | Done
Check suricata alerts log on SJOMO, SMAMO, CODC, and reply to Raghavendra - Waiting for IPs from PRIME | Achyut Deshpande | 2024-06-14
Delete counter tables for AVH jan and dec | Manoj Singh | 2024-06-14 | Done
Follow up on whitelisting OpenAI with AVH | Achyut Deshpande | 2024-06-14 | Done
Delete alerts on AVH from Cassandra | Naveen Adusumilli | 2024-06-14 | Done
Darkeye Production- Reports not working | Naveen Adusumilli | 2024-06-14 | Done
Darkeye Mongo Db Upgrade further- ON HOLD | Gopalswamy Ramalingam | 2024-06-14
reply Mahender for suricata.yml files | Thota | 2024-06-14 | Done
reply Mahender for suricata.yml files | Gopalswamy Ramalingam | 2024-06-14 | Done
reply Mahender for suricata.yml files | Kishore Aerravelly | 2024-06-14 | Done
Mount radio folder- Pulse Prime- Thota Following up with Raghu | Achyut Deshpande | 2024-06-14 | Done
Test the Ask Pulse module on AVH | Sneha Guthe | 2024-06-19 | Done
Research on Alerting on resources Threshold for Pulse | Gopalswamy Ramalingam | 2024-06-24
Offline Swimlane deployment- Testing Pending by Thota | Thota | 2024-07-01
Delete counter tables data older than 3 months Prime | Manoj Singh | 2024-06-14 | Done
Datacenters onboard pending- VLans not visible - PENDING FROM PRIME | Achyut Deshpande | 2024-06-14 | On Hold
Datacenters onboard pending- VLans not visible - PENDING FROM PRIME | Sai Sampath Chinthavatla | 2024-06-14 | On Hold
IOE Risk in AVH - give revenue details to Ajay | Shrashti Singhal | 2024-06-20 | Done
Change file beat for the facilities found incorrect in testing | Sai Sampath Chinthavatla | 2024-06-19 | Done
Unnamed | Sneha Guthe | 2024-05-15 | Done
Check suricata alerts log on SJOMO, SMAMO, CODC, and reply to Raghavendra - Waiting for IPs from PRIME | Achyut Deshpande | 2024-06-05 | On Hold
Darkeye Mongo Db Upgrade further- ON HOLD | Gopalswamy Ramalingam | 2024-06-21 | On Hold
Open url's for Darkeye for sentimind avatar confirmation(Varad's email on 12th June) | Thota | 2024-06-21 | On Hold
Filebeat automation | Somesh Fengade | 2024-06-20
Darkeye at AVH- connect with the client for setting up demo | Shrashti Singhal | 2024-06-21 | Done
test 6.0.19 suricata version in a docker image | Achyut Deshpande | 2024-06-20 | Done
Filebeat testing for updated Filebeat | Sneha Guthe | 2024-06-21 | Done
Run fingerprints pattern mining on AVH device summary | Shrashti Singhal | 2024-06-21 | Done
Test filebeats generated by code | Somesh Fengade | 2024-06-21
Test filebeats generated by code | Sneha Guthe | 2024-06-21
Test filebeats generated by code | Sai Sampath Chinthavatla | 2024-06-21
Upgrade suricata on all sensors- ON HOLD | Sai Sampath Chinthavatla | 2024-06-21
Upgrade suricata on all sensors- ON HOLD | Achyut Deshpande | 2024-06-21
Snort bot, huge number of alerts | Naveen Adusumilli | 2024-06-21
Snort bot, huge number of alerts | Ajay kumar | 2024-06-21
Verify the format of Devices Summary on AVH (compare with Pulse) | Naveen Adusumilli | 2024-06-21 | Done
Looking into spark logs, kafka feed and Cassandra Tables for Snort | Naveen Adusumilli | 2024-06-21
DNS restart issue | Naveen Adusumilli | 2024-06-21
Set up Alerts on Cassandra Pulse Prime (teams alerts) | Gopalswamy Ramalingam | 2024-06-21 | Done
Set up Alerts on Cassandra Pulse Prime (teams alerts) | Achyut Deshpande | 2024-06-21 | Done
Set up alternate Cassandra environment for auto deletion counter tables query | Gopalswamy Ramalingam | 2024-06-21
Look into the ratio of storage for Events vs Counter Tables for 3 months (90 days) | Naveen Adusumilli | 2024-06-21
Look into the ratio of storage for Events vs Counter Tables for 3 months (90 days) | Achyut Deshpande | 2024-06-21
Research on Alerting on resources Threshold for Pulse | Gopalswamy Ramalingam | 2024-07-03 | To do
Offline Swimlane deployment- Testing Pending by Thota | Thota | 2024-07-01
Datacenters onboard pending- VLans not visible - PENDING FROM PRIME | Sai Sampath Chinthavatla | 2024-06-28 | On Hold
Datacenters onboard pending- VLans not visible - PENDING FROM PRIME | Achyut Deshpande | 2024-06-28 | On Hold
Check suricata alerts log on SJOMO, SMAMO, CODC, and reply to Raghavendra - Waiting for IPs from PRIME | Achyut Deshpande | 2024-06-05 | On Hold
Darkeye Mongo Db Upgrade further- ON HOLD | Gopalswamy Ramalingam | 2024-06-28 | On Hold
Filebeat automation | Somesh Fengade | 2024-06-20 | In Progress
Test filebeats generated by code | Somesh Fengade | 2024-06-21 | In Progress
Test filebeats generated by code | Sneha Guthe | 2024-06-21 | In Progress
Test filebeats generated by code | Sai Sampath Chinthavatla | 2024-06-21 | In Progress
Upgrade suricata on all sensors- ON HOLD | Achyut Deshpande | 2024-06-21 | On Hold
Upgrade suricata on all sensors- ON HOLD | Sai Sampath Chinthavatla | 2024-06-21 | On Hold
Snort bot, huge number of alerts | Naveen Adusumilli | 2024-06-21 | Done
Snort bot, huge number of alerts | Ajay kumar | 2024-06-21 | Done
Looking into spark logs, kafka feed and Cassandra Tables for Snort | Naveen Adusumilli | 2024-06-21 | Done
DNS restart issue- Cassandra addition of more nodes | Naveen Adusumilli | 2024-06-21
DNS restart issue- Cassandra addition of more nodes | Achyut Deshpande | 2024-06-21
Set up alternate Cassandra environment for auto deletion counter tables query | Gopalswamy Ramalingam | 2024-06-21 | Done
Look into the ratio of storage for Events vs Counter Tables for 3 months (90 days) | Achyut Deshpande | 2024-06-21 | On Hold
Look into the ratio of storage for Events vs Counter Tables for 3 months (90 days) | Naveen Adusumilli | 2024-06-21 | On Hold
Not receiving teams alerts on storage. Please verify it for Prime and AVH | Sai Sampath Chinthavatla | 2024-06-28 | Done
Not receiving teams alerts on storage. Please verify it for Prime and AVH | Achyut Deshpande | 2024-06-28 | Done
Setting up new Node for Cassandra Prime Production | Gopalswamy Ramalingam | 2024-06-28 | Done
Setting up new Node for Cassandra Prime Production | Naveen Adusumilli | 2024-06-28 | Done
Alerts on AVH and Prime for Server Storage | Achyut Deshpande | 2024-06-28 | Done
Alerts on AVH and Prime for Server Storage | Sai Sampath Chinthavatla | 2024-06-28 | Done
Alerts on AVH and Prime for Server Storage | Sneha Guthe | 2024-06-28 | Done
Setting up rules on Prime Alerts | Achyut Deshpande | 2024-06-28 | Done
Setting up rules on Prime Alerts | Ajay kumar | 2024-06-28 | Done
Remove 1M alerts from AVH | Naveen Adusumilli | 2024-06-28
Test auto deletion of counter tables script | Varad Bhalsing | 2024-06-28
Emergency Channel or emergency alerts on Teams | Sai Sampath Chinthavatla | 2024-06-28
AVH and Prime Production Deployment | Gopalswamy Ramalingam | 2024-07-01
AVH and Prime Production Deployment | Naveen Adusumilli | 2024-07-01