## Loop Tasks
Resource Name | Tasks List | Status | Date
Sai Sampath | Look into the revenue/charges sheet for Prime | Done | 2024-03-05
Ajay | Cron job for IOC parser Darkeye |  | 2024-03-05
Ajay | Export functionality recent dates Pulse Demo, test today |  | 2024-03-05
Mahesh | Social Media Design Development |  | 2024-03-05
Somesh | Social media Data Visualization continue | Done | 2024-03-05
Varad | Social Media Production Code Merge con | Done | 2024-03-05
Ritika | Complete remaining Social Media Design | Done | 2024-03-05
Suyash | Complete remaining Social Media Design | Done | 2024-03-05
Achyut | Sys log Alerts filters on all sensors, mail Prime Team | Done | 2024-03-05
Gopal | Pulse Deployment changes | Done | 2024-03-05
Gopal | Kafka Monitoring integration with Graffana was done, blocker because performance, that's why reverted changes |  | 2024-03-05
Mahesh | Change ThreatPrism Logo |  | 2024-03-05
Ajay | Scan ending, End points integration DarkEye |  | 2024-03-05
Varad | Scan ending, End points integration DarkEye |  | 2024-03-05
Gopal | Deploy Threat Prism Backend | Done | 2024-03-05
Naveen | Pulse - EPSS and KEV Integration - Go over the blockers |  | 2024-03-05
Mahesh | Fix Pulse demo date issue | Done | 2024-03-05
Sneha | Test the Pulse demo date issue | Done | 2024-03-05
Manoj | Create dummy data for Pulse demo |  | 2024-03-05
Shrashti | Create dummy data for Pulse demo |  | 2024-03-05
Gopal | formflow.ai POC Questionnaire, Clarification call |  | 2024-03-05
Thota | change DNS servers Pulse; need confirmation who needs to execute it |  | 2024-03-05
Manoj | Send Data for Snort Alerts for Prime Prod and AVH prod to Palan | Done | 2024-03-05
Manoj | Research on integration of matomo and mouseflow behavior analytics with Darkeye |  | 2024-03-05
Gopal | Darkeye VM Resize | Done | 2024-03-05
Gopal | GIT PR Process to be implemented for dev and qa branches | Done | 2024-03-05
Sneha | Send an Email for Approval for PROD Deployment | Done | 2024-03-05
Sneha | Test the Darkeye PROD environment once the changes Deployed | Done | 2024-03-05
Achyut | Please deploy backend & frontend of ThreatPrism on https://threatprism.culinda.com/ instead of https://threatprismfrontend.z13.web.core.windows.net/ | Done | 2024-03-05
Sneha | Verify the Revenue’s of Site from the UI | Done | 2024-03-05
Palan | Reports Review |  | 2024-03-05
Sneha | Test the Pulse Demo - Date Issue | Done | 2024-03-05
Sai Sampath | Look into the revenue/charges sheet for Prime |  | 2024-03-06
Achyut | Look into the revenue/charges sheet for Prime |  | 2024-03-06
Ajay | Cron job for IOC parser Darkeye |  | 2024-03-06
Mahesh | Social Media Design Development |  | 2024-03-06
Varad | Social Media Production Code Merge continue |  | 2024-03-06
Jatin | Social Media Production Code Merge continue |  | 2024-03-06
Achyut | Sys log, please get back to Nagraj |  | 2024-03-06
Gopal | Kafka Monitoring integration with Graffana was done, blocker because performance, that's why reverted changes |  | 2024-03-06
Achyut | Create Kafka Graffana Dashboards |  | 2024-03-06
Mahesh | Change ThreatPrism Logo | Done | 2024-03-06
Mahesh | Make the ThreatPrism UI responsive |  | 2024-03-06
Palan | Scan ending, End points integration DarkEye |  | 2024-03-06
Sneha | Document Feedback review on Darkeye from Prime Team Demo | Done | 2024-03-06
Manoj | Research on integration of matomo and mouseflow behavior analytics with Darkeye | Done | 2024-03-06
Sneha | Please send DARKEYE SPRINT report. | Done | 2024-03-06
Palan | Review Reports by Deena | Done | 2024-03-06
Sneha | Test the Pulse Demo | Done | 2024-03-06
Shrashti | Send Updated asset inventory to Manoj for Pulse Demo | Done | 2024-03-06
Manoj | Upload asset inventory to Pulse Demo | Done | 2024-03-06
Shrashti | Send meta data sheet to upload in pulse Demo to Naveen/Amitabh | Done | 2024-03-06
Ajay | Pulse demo Online devices issues in GRID | Done | 2024-03-06
Ajay | Pulse demo GRID view Risk score |  | 2024-03-06
Somesh | Add research papers to Threat Prism Vector DB | Done | 2024-03-06
Gopal | GCP |  | 2024-03-07
Raghu | Look into the revenue/charges sheet for Prime |  | 2024-03-07
Varad | Social Media Production Code Merge continue | Done | 2024-03-07
Jatin | Social Media Production Code Merge continue | Done | 2024-03-07
Achyut | Sys log, please get back to Nagraj | Done | 2024-03-07
Mahesh | Make the ThreatPrism UI responsive |  | 2024-03-07
Saradhi | Threat Prism Streaming response |  | 2024-03-07
Somesh | Threat Prism Streaming response |  | 2024-03-07
Palan | Scan ending, End points integration DarkEye |  | 2024-03-07
Ajay | Scan ending, End points integration DarkEye |  | 2024-03-07
Sneha | Test Reports by Deena |  | 2024-03-07
Sneha | Test the Pulse Demo | Done | 2024-03-07
Shrashti | Test the Pulse Demo | Done | 2024-03-07
Naveen | upload meta data on Pulse Demo | Done | 2024-03-07
Amitabh | upload meta data on Pulse Demo | Done | 2024-03-07
Ajay | Pulse demo Add GRID view Risk$ and Likelihood | Done | 2024-03-07
Saradhi | Pulse demo Add GRID view Risk$ and Likelihood | Done | 2024-03-07
Achyut | Pulse Production Alerts missing from 4th March |  | 2024-03-07
Palan | Pulse Production Alerts missing from 4th March |  | 2024-03-07
Amitabh | New features to persist domain Reputation score for every scan in db | Done | 2024-03-07
Kishore | Working on creating documentation requested by Nikhil for architecture refinement | Done | 2024-03-07
Kishore | Keycloak authentication mechanism for Azure functions to access webhook |  | 2024-03-07
Thota | Review adding of KEV & EPSS fields in Cassandra, confirmation on purging and creating new table | Done | 2024-03-07
Thota | Purge Data as we can fetch same Data from Tenable using existing daily batch job. | Done | 2024-03-07
Thota | Review of MouseFlow with Manoj, if it adds vulnerability to Darkeye - Went over Architecture and implementation, need to pentest application , please add a task to perform Pentest - I will take care | Done | 2024-03-07
Ritika | Create Zone Transfer design and send for taking approval | Done | 2024-03-07
Ajay | Fix new device widgets after inserting asset inventory data in demo Pulse |  | 2024-03-07
Mahesh | Add dollar sign to Asset Value- Pulse demo | Done | 2024-03-07
Ajay | Categories by VLAN not working- Pulse Demo | Done | 2024-03-07
Ajay | Bubble view Sensor Mangement- Pulse Demo | Done | 2024-03-07
Mahesh | Bubble view Sensor Mangement- Pulse Demo | Done | 2024-03-07
Mahesh | Camel Case, alerts by severity table- Pulse Demo | Done | 2024-03-07
Mahesh | Changing of Device Alerts Comparision Widget- Pulse Demo | Done | 2024-03-07
Ajay | Risk by Data Values bar chart not showing correct Risk Values- Pulse Demo | Done | 2024-03-07
Saradhi | Risk by Data Values bar chart not showing correct Risk Values- Pulse Demo | Done | 2024-03-07
Ajay | Online devices in Grid View not working-Pulse Demo | Done | 2024-03-07
Ajay | New Devices in Grid View not working- Pulse Demo | Done | 2024-03-07
Thota | Extracting Vulnerabilities sample data | Done | 2024-03-07
Naveen | Extracting Vulnerabilities sample data | Done | 2024-03-07
Achyut | Please provide the list of sensors to Raghu which are not receiving the Revenue data | Done | 2024-03-08
Raghu | Please provide the list of sensors to Raghu which are not receiving the Revenue data | Done | 2024-03-08
Gopal | GCP |  | 2024-03-08
Varad | Social Media Production Code change in code for multiple hashtags continue |  | 2024-03-08
Jatin | Social Media Production Code change in code for multiple hashtags continue |  | 2024-03-08
Achyut | Sys log, please get back to Nagraj, call with Prime Team today |  | 2024-03-08
Gopal | Threat Prism Streaming response | Done | 2024-03-08
Saradhi | Threat Prism Streaming response | Done | 2024-03-08
Mahesh | Threat Prism Streaming response | Done | 2024-03-08
Palan | Scan ending, End points integration DarkEye - continue |  | 2024-03-08
Naveen | Scan ending, End points integration DarkEye - continue |  | 2024-03-08
Sneha | Test Reports by Deena |  | 2024-03-08
Achyut | Pulse Production Alerts missing from 4th March- file beat configuration |  | 2024-03-08
Kishore | deliver/email to Nikhil- documentation of architecture |  | 2024-03-08
Kishore | Keycloak authentication mechanism for Azure functions to access webhook |  | 2024-03-08
Thota | Updates on Mouseflow after Pen testing |  | 2024-03-08
Ritika | Please provide design access (zone transfer) | Done | 2024-03-08
Saradhi | Severity Drill downs - Pulse Demo | Done | 2024-03-08
Ajay | Linking CVEs with tenable page for information Pulse- Demo | Done | 2024-03-08
Ajay | Re-order data to show inbound, graphs and other fields- Pulse Demo | Done | 2024-03-08
Saradhi | Re-order fields of CVE table to show IP & MAC after CVE ID | Done | 2024-03-08
Saradhi | Dollar sign before the asset value & risk fields- Pulse Demo | Done | 2024-03-08
Ajay | Ask Pulse- please check for Medical Tag in inventory- Pulse Demo |  | 2024-03-08
Saradhi | Merge NDR Alerts & Alerts BY Severity Widgets-Pulse Demo | Done | 2024-03-08
Ritika | Design Development, add handles, keywords etc. in Add domain- Darkeye |  | 2024-03-08
Suyash | Design Development, add handles, keywords etc. in Add domain- Darkeye |  | 2024-03-08
Manoj | Send snort alerts (5th march to 7th march) for AVH prod to Palan | Done | 2024-03-08
Sneha | Test the Pulse Demo once the Changes Are Done which is suggested By Uma | Done | 2024-03-08
Sneha | Make a list of tasks from the 1st March of all the Resources & share with Shrashti | Done | 2024-03-08
Naveen | Uploaded meta data for missing 2 fields in Pulse Demo | Done | 2024-03-08
Amitabh | Uploaded meta data for missing 2 fields in Pulse Demo | Done | 2024-03-08
Shrashti | Edit Meta data to fix email address in 4 fields and add 2 fields asset access & communication Layer | Done | 2024-03-08
Naveen | Upload meta data again to reflect changes- Pulse Demo | Done | 2024-03-08
Amitabh | Upload meta data again to reflect changes- Pulse Demo | Done | 2024-03-08
Thota | Review Gopals GCP document |  | 2024-03-11
Achyut | Pulse Production Alerts missing from 4th March- file beat configuration |  | 2024-03-11
Palan | Pulse Production Alerts missing from 4th March- file beat configuration |  | 2024-03-11
Varad | Social Media Production Code change in code for multiple hashtags continue- SPRINTS TASK | Done | 2024-03-11
Jatin | Social Media Production Code change in code for multiple hashtags continue- SPRINTS TASK | Done | 2024-03-11
Gopal | Sys log, please get back to Nagraj, call with Prime Team today |  | 2024-03-11
Palan | Scan ending, End points integration DarkEye - continue |  | 2024-03-11
Sneha | Test Reports by Deena |  | 2024-03-11
Kishore | deliver/email to Nikhil- documentation of architecture | Done | 2024-03-11
Kishore | Keycloak authentication mechanism for Azure functions to access webhook | Done | 2024-03-11
Thota | Updates on Mouseflow after Pen testing |  | 2024-03-11
Thota | Review Gopals GCP document |  | 2024-03-12
Achyut | Pulse Production Alerts missing from 4th March- file beat configuration |  | 2024-03-12
Palan | Pulse Production Alerts missing from 4th March- file beat configuration |  | 2024-03-12
Gopal | Sys log, please get back to Nagraj, call with Prime Team today |  | 2024-03-12
Palan | Scan ending, End points integration DarkEye - continue | Done | 2024-03-12
Varad | Scan ending, End points integration DarkEye - continue | Done | 2024-03-12
Naveen | Scan ending, End points integration DarkEye - continue | Done | 2024-03-12
Gopal | Updates on Mouseflow after adding CORS |  | 2024-03-12
Manoj | Help Somesh setup MongoDB on dev | Done | 2024-03-12
Achyut | Help Somesh setup MongoDB on dev | Done | 2024-03-12
Thota | Review Gopals GCP document |  | 2024-03-13
Achyut | Pulse Production Alerts missing from 4th March- file beat configuration | Done | 2024-03-13
Naveen | Pulse Production Alerts missing from 4th March- file beat configuration | Done | 2024-03-13
Gopal | Sys log, please get back to Nagraj, call with Prime Team today |  | 2024-03-13
Gopal | Adding CORS to Darkeye Research | Done | 2024-03-13
Achyut | Sys log, please get back to Nagraj |  | 2024-03-14
Gopal | Sys log, please get back to Nagraj |  | 2024-03-14
Achyut | Provide the known_devices dump from Prime Pulse production to shrashti to less devices tasks | Done | 2024-03-14
Mahesh | Make the ThreatPrism UI responsive |  | 2024-03-14
Achyut | Sys log 4 sensors pending |  | 2024-03-15
Ritika | Give threatPrism svg logo to Mahesh | Done | 2024-03-15
Mahesh | URL icon of Threat Prism is a robot currently, Please replace by Raghu's logo (svg given by Ritika) |  | 2024-03-15
Sneha | Test python cookies code for Linkedin | Done | 2024-03-15
Shrashti | Match of Devices (known_device) with IP subnets |  | 2024-03-15
Sneha | Provide access to the user as requested by Shashi & Informed them over the email | Done | 2024-03-15
Sneha | Send the All Vendor list to Thota for his review | Done | 2024-03-15
Sneha | Compare the List provide by Arul (Are the domains are already in DB or not ?) | Done | 2024-03-15
Manoj | Need to provide vendors list of Primehealthcare to Sneha | Done | 2024-03-15
Achyut | Sys log 4 sensors pending |  | 2024-03-18
Gopal | Sys log 4 sensors pending |  | 2024-03-18
Mahesh | URL icon of Threat Prism is a robot currently, Please replace by Raghu's logo (svg given by Ritika | Done | 2024-03-18
Jatin | Test python cookies code for Linkedin | Done | 2024-03-18
Shrashti | Match of Devices (known_device) with IP subnets from Shashi | Done | 2024-03-18
Kishore | Match of Devices (known_device) with IP subnets from Uma for Data Centers |  | 2024-03-18
Sneha | Remaining domains have to fill missing details |  | 2024-03-18
Shrashti | Remaining domains have to fill missing details |  | 2024-03-18
Achyut | AVH bots arent running | Done | 2024-03-18
Gopal | Look into the threatprism api end point |  | 2024-03-18
Somesh | Look into the threatprism api end point |  | 2024-03-18
Manoj | Change Darkeye Passwords prod customers. common logins | Done | 2024-03-18
Manoj | Change Password VRM Darkeye | Done | 2024-03-18
Ajay | Pulse demo change passwords | Done | 2024-03-18
Ritika | New design for User account handles- social media functionality |  | 2024-03-18
Suyash | New design for User account handles- social media functionality |  | 2024-03-18
Manoj | Test the AVH bots again and confirm if they are working | Done | 2024-03-18
Achyut | Please provide master vlan sheet to Shrashti | Done | 2024-03-18
Somesh | Please provide master vlan sheet to Shrashti | Done | 2024-03-18
Gopal | Sys log 4 sensors pending |  | 2024-03-19
Kishore | Sys log 4 sensors pending |  | 2024-03-19
Thota | Sys log 4 sensors pending |  | 2024-03-19
Sneha | Remaining domains have to fill missing details (org type & service type, address). |  | 2024-03-19
Kishore | Match of Devices (known_device) with IP subnets from Uma for Data Centers |  | 2024-03-19
Somesh | Look into the threatprism api end point | Done | 2024-03-19
Ritika | New design for User account handles- social media functionality |  | 2024-03-19
Suyash | New design for User account handles- social media functionality |  | 2024-03-19
Shrashti | Get subnets & IP addresses from Prime Team |  | 2024-03-19
Kishore | Onboard servers and analyse traffic |  | 2024-03-19
Achyut | Onboard servers and analyse traffic |  | 2024-03-19
Gopal | Sys log 4 sensors pending |  | 2024-03-20
Sneha | Remaining domains have to fill missing details (org type & service type, address). | Done | 2024-03-20
Kishore | Match of Devices (known_device) with IP subnets from Uma for Data Centers |  | 2024-03-20
Somesh | Look into the threatprism api end point |  | 2024-03-20
Ritika | New design for User account handles- social media functionality |  | 2024-03-20
Suyash | New design for User account handles- social media functionality |  | 2024-03-20
Shrashti | Get subnets & IP addresses from Prime Team |  | 2024-03-20
Kishore | Onboard servers and analyse traffic |  | 2024-03-20
Achyut | Onboard servers and analyse traffic |  | 2024-03-20
Kishore | SBOM follow up |  | 2024-03-20
Gopal | SBOM follow up |  | 2024-03-20
Sneha | Deployment Testing- Darkeye | Done | 2024-03-20
Varad | Zone transfer response research |  | 2024-03-20
Somesh | NAICS Code help |  | 2024-03-20
Sneha | Create the list of users which need to be deleted from Darkeye & Pulse PROD | Done | 2024-03-20
Gopal | Sys log 4 sensors pending |  | 2024-03-21
Sneha | Initiate scan for bulk Upload- Darkeye |  | 2024-03-21
Naveen | Initiate scan for bulk Upload- Darkeye |  | 2024-03-21
Kishore | Match of Devices (known_device) with IP subnets from Uma for Data Centers |  | 2024-03-21
Kishore | SBOM backward compatibility issue |  | 2024-03-21
Naveen | SBOM backward compatibility issue |  | 2024-03-21
Varad | Zone transfer response research | Done | 2024-03-21
Palan | Zone transfer response research | Done | 2024-03-21
Somesh | NAICS Code help | Done | 2024-03-21
Naveen | Initiate scan for bulk Upload- Darkeye |  | 2024-03-22
Kishore | Match of Devices (known_device) with IP subnets from Uma for Data Centers |  | 2024-03-22
Kishore | SBOM backward compatibility issue | Done | 2024-03-22
Naveen | SBOM backward compatibility issue | Done | 2024-03-22
Varad | Zone transfer response research |  | 2024-03-22
Palan | Zone transfer response research |  | 2024-03-22
Somesh | NAICS Code help |  | 2024-03-22
Manoj | Snorts logs- give to Palan to Review | Done | 2024-03-22
Shrashti | remove DNS Events in AVH- storage issues- approval | Done | 2024-03-22
Gopal | Social Media provide VM |  | 2024-03-22
Gopal | LinkedIn login in Darkeye Dev |  | 2024-03-22
Gopal | Form Flow AI - Interaction with Vendor | Done | 2024-03-22
Varad | Setting up Social Media code in VM | Done | 2024-03-22
Somesh | Setting up Social Media code in VM | Done | 2024-03-22
Somesh | NAICS code/Write Api integration | Done | 2024-03-26
Achyut | AVH logs storage issue- KT on procedure to clean up the tables every month to | Done | 2024-03-26
Kishore | AVH logs storage issue- KT on procedure to clean up the tables every month to | Done | 2024-03-26
Manoj | AVH logs storage issue- KT on procedure to clean up the tables every month to | Done | 2024-03-26
Achyut | Prime snort logs - find the sensors with old rules and remove them | Done | 2024-03-26
Naveen | Domain scan request Azul- to be discussed | Done | 2024-03-26
Thota | Domain scan request Azul- to be discussed | Done | 2024-03-26
Manoj | New domain scan request by Nagraj | Done | 2024-03-26
Ajay | Cron job for IOC parser- moved to Sprint | Done | 2024-03-26
Varad | News feed- check for subscription | Done | 2024-03-26
Gopal | Sys log 4 sensors issues |  | 2024-03-26
Gopal | Forms AI | Done | 2024-03-26
Gopal | Onboarding 3 data centers-sensors, Zeek is working on 1 sensor now |  | 2024-03-26
Sneha | Scan domain add details for bulk upload template | Done | 2024-03-26
Manoj | Scan domain add details for bulk upload template | Done | 2024-03-26
Saradhi | Zone transfer- Part of Sprint | Done | 2024-03-26
Naveen | Rapid 7 AVH |  | 2024-03-26
Shrashti | ProdSupport@culinda.com to add in all clients email |  | 2024-03-26
Naveen | upload vendor point of contact- Darkeye |  | 2024-03-26
Gopal | GCP meeting | Done | 2024-03-26
Thota | GCP meeting | Done | 2024-03-26
Thota | Review Gopals GCP document | Done | 2024-03-26
Manoj | provide Snort Logs dump to Palan | Done | 2024-03-27
Gopal | will work on Form apis |  | 2024-03-27
Gopal | Sys log 4 sensors issues |  | 2024-03-27
Gopal | Onboarding 3 data centers-sensors, Zeek is working on 1 sensor now |  | 2024-03-27
Somesh | Generate master_vlans.csv for new IP subnets | Done | 2024-03-27
Naveen | Rapid 7 AVH |  | 2024-03-27
Shrashti | ProdSupport@culinda.com to add in all clients email |  | 2024-03-27
Naveen | upload vendor point of contact- Darkeye |  | 2024-03-27
Manoj | provide NAICS categories and sub category dump to Shrashti | Done | 2024-03-27
Gopal | will work on Form apis |  | 2024-03-28
Gopal | Sys log 4 sensors issues |  | 2024-03-28
Gopal | Onboarding 3 data centers-sensors, Zeek is working on 1 sensor now |  | 2024-03-28
Somesh | Generate master_vlans.csv for new IP subnets recheck | Done | 2024-03-28
Naveen | Rapid 7 AVH |  | 2024-03-28
Shrashti | ProdSupport@culinda.com to add in all clients email |  | 2024-03-28
Naveen | upload vendor point of contact- Darkeye |  | 2024-03-28
Manoj | Debug google Analytics |  | 2024-03-28
Shrashti | Debug google Analytics |  | 2024-03-28
Manoj | Send 27th March 2024 snort alerts of Prime prod to Palan | Done | 2024-03-28
Gopal | Suricata- sys log issue |  | 2024-03-28
Gopal | Sys log 4 sensors issues |  | 2024-03-29
Gopal | Onboarding 3 data centers-sensors, Zeek is working on 1 sensor now |  | 2024-03-29
Gopal | Form apis |  | 2024-03-29
Shrashti | ProdSupport@culinda.com to add in all clients email |  | 2024-03-29
Sneha | Domain typo Squatting | Done | 2024-03-29
Varad | Fastapi bulk scan issue |  | 2024-03-29
Palan | Fastapi bulk scan issue |  | 2024-03-29
Ajay | Cron Job for IOC parser docker deployment | Done | 2024-03-29
Palan | Cron Job for IOC parser docker deployment | Done | 2024-03-29
Shrashti | Analyse Industry and service type NAICS categories already in Darkeye |  | 2024-03-29
Ajay | Aggregate tables for Pulse, need daily count |  | 2024-03-29
Sneha | Test the Sprint Tasks

## Sheet1
Issue Type | Count of Summary
Bug | 20
Story | 3
Subtask | 28
Task | 32

## Sheet2
Sprint | Count of Summary
DarkEye Bulk Automation | 1
DarkEye Performance | 31
Darkeye Performance Enhancemen | 24
(blank) | 27

## Sheet3
Row Labels | Count of Summary
0 | 1
0 | 1
Done | 69
Ajay Kumar Devarakonda | 7
Amitabh Sharma | 1
Kishore Aerravelly | 3
Mahesh Katti | 1
Manoj Singh Rawat | 7
Naveen Adusumilli | 7
Palaniyappan Bala | 1
Ritika | 3
SaradhiMuneendra Gundabattina | 12
Sneha Sonyabapu Guthe | 8
Somesh Fengade | 2
V Thota | 1
Varad Balasaheb Bhalsing | 2
(blank) | 14
Move To PROD | 6
Ajay Kumar Devarakonda | 1
Naveen Adusumilli | 1
SaradhiMuneendra Gundabattina | 4
Not Required/Duplicate | 1
Naveen Adusumilli | 1
To Do | 7
Naveen Adusumilli | 4
SaradhiMuneendra Gundabattina | 1
Varad Balasaheb Bhalsing | 2
Grand Total | 84

## Sheet4
Row Labels | Count of Summary
0 | 1
0 | 1
Ajay Kumar Devarakonda | 8
Done | 7
Move To PROD | 1
Amitabh Sharma | 1
Done | 1
Kishore Aerravelly | 3
Done | 3
Mahesh Katti | 1
Done | 1
Manoj Singh Rawat | 7
Done | 7
Naveen Adusumilli | 13
Done | 7
Move To PROD | 1
Not Required/Duplicate | 1
To Do | 4
Palaniyappan Bala | 1
Done | 1
Ritika | 3
Done | 3
SaradhiMuneendra Gundabattina | 17
Done | 12
Move To PROD | 4
To Do | 1
Sneha Sonyabapu Guthe | 8
Done | 8
Somesh Fengade | 2
Done | 2
V Thota | 1
Done | 1
Varad Balasaheb Bhalsing | 4
Done | 2
To Do | 2
(blank) | 14
Done | 14
Grand Total | 84

## Sprint Tasks
Summary | Issue key | Issue Type | Status | Assignee | Created | Updated | Last Viewed | Sprint | Sprint
Bulk Upload & Scanning of the Domain the list provide by Prime Team. | DPI-104 | Task | Done | Sneha Sonyabapu Guthe | 2024-03-27 23:35 | 2024-03-28 09:52 | 2024-04-03 06:31
Validated the News Feed using the Feedspot API with Darkeye PROD UI . | DPI-103 | Task | Done | Sneha Sonyabapu Guthe | 2024-03-27 23:34 | 2024-03-28 09:52 | 2024-03-27 23:35
Add Time Zone under the Email Templates. | DPI-102 | Task | To Do | Naveen Adusumilli | 2024-03-20 11:08 | 2024-03-20 11:08 | 2024-04-03 06:31
Add stricter rules of screen recording given by Mouse flow | DPI-101 | Subtask | Done | Manoj Singh Rawat | 2024-03-16 07:33 | 2024-04-03 00:26 | 2024-04-03 06:31 | DarkEye Performance
Add cookies for user consent for screen recording | DPI-100 | Subtask | Done | SaradhiMuneendra Gundabattina | 2024-03-16 07:33 | 2024-04-03 00:26 | 2024-04-03 06:31 | DarkEye Performance
Swimlane Integrations | DPI-99 | Task | To Do | Varad Balasaheb Bhalsing | 2024-03-15 00:10 | 2024-03-18 01:28 | 2024-03-20 11:08
Add cron job to update IOC parser details regularly | DPI-98 | Task | Move To PROD | Ajay Kumar Devarakonda | 2024-03-15 00:09 | 2024-03-29 06:50 | 2024-04-02 22:49 | DarkEye Performance
Need to change scrip to get json output | DPI-97 | Subtask | Done | Varad Balasaheb Bhalsing | 2024-03-11 23:21 | 2024-03-28 06:17 | 2024-04-03 06:31 | DarkEye Performance
Bulk Scan | DPI-96 | Task | To Do | Naveen Adusumilli | 2024-03-07 22:37 | 2024-04-02 02:34 | 2024-04-03 06:31 | DarkEye Bulk Automation
Create a scheduled job every 12:02 am IST | DPI-95 | Subtask | Done | Ajay Kumar Devarakonda | 2024-03-07 08:42 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Store Sentiments received from the code to Mongo DB | DPI-94 | Subtask | Done | Ajay Kumar Devarakonda | 2024-03-07 08:41 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Take data from Mongo DB and pass to Sentiment analysis Code | DPI-93 | Subtask | Done | Ajay Kumar Devarakonda | 2024-03-07 08:38 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Create Sentiment Analysis Code | DPI-92 | Subtask | Done | Somesh Fengade | 2024-03-07 08:37 | 2024-04-02 22:48 | 2024-04-03 06:31 | DarkEye Performance
Create MYSQL table to store Client hashtags, handles, keywords | DPI-91 | Subtask | Done | Kishore Aerravelly | 2024-03-07 08:31 | 2024-03-17 22:58 | 2024-04-03 06:31 | DarkEye Performance
Take input from DB(per user) and pass to code | DPI-90 | Subtask | Done | Ajay Kumar Devarakonda | 2024-03-07 08:29 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Take User Inputs of handles and pass to code/utility | DPI-89 | Subtask | Done | Kishore Aerravelly | 2024-03-07 08:26 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Develop the designs to add handles | DPI-88 | Subtask | Done | SaradhiMuneendra Gundabattina | 2024-03-07 08:25 | 2024-03-18 22:48 | 2024-04-03 06:31 | DarkEye Performance
Create Design to add handles, accounts, hashtags and keywords | DPI-87 | Subtask | Done | Ritika | 2024-03-07 08:25 | 2024-03-12 06:10 | 2024-04-03 06:31 | DarkEye Performance
Allow User to Add handles, accounts, hashtags and keyword Module to add domain | DPI-86 | Story | Move To PROD | SaradhiMuneendra Gundabattina | 2024-03-07 08:24 | 2024-04-02 08:50 | 2024-04-03 06:29 | DarkEye Performance
Integrate Mongo DB Queries to Frontend | DPI-85 | Subtask | Done | SaradhiMuneendra Gundabattina | 2024-03-07 08:23 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Use json queries to create service layer queries to create Mongo DB queries for Widgets | DPI-84 | Subtask | Done | Naveen Adusumilli | 2024-03-07 08:21 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Create json visualization queries for each widget | DPI-83 | Subtask | Done | Somesh Fengade | 2024-03-07 08:20 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Purge extracted data from social media(json) to Mongo DB collections | DPI-82 | Subtask | Done | Manoj Singh Rawat | 2024-03-07 08:20 | 2024-04-02 22:48 | 2024-04-03 06:31 | DarkEye Performance
Create Mongo DB Collections to store Social Media Extracted Data | DPI-81 | Subtask | Done | Manoj Singh Rawat | 2024-03-07 08:19 | 2024-04-02 22:48 | 2024-04-03 06:31 | DarkEye Performance
Code to extract Social Media Posts | DPI-80 | Subtask | Done | Varad Balasaheb Bhalsing | 2024-03-07 08:18 | 2024-03-18 08:03 | 2024-04-03 06:31 | DarkEye Performance
Develop Social Media Design Page | DPI-79 | Subtask | Done | Mahesh Katti | 2024-03-07 08:16 | 2024-04-02 22:48 | 2024-04-03 06:31 | DarkEye Performance
Design Social Media Design Page | DPI-78 | Subtask | Done | Ritika | 2024-03-07 08:16 | 2024-03-11 23:05 | 2024-04-03 06:31 | DarkEye Performance
Add Client Social Media Sentiment Tracker Page to Darkeye | DPI-77 | Story | Move To PROD | SaradhiMuneendra Gundabattina | 2024-03-07 08:14 | 2024-04-02 03:03 | 2024-04-02 22:48 | DarkEye Performance
Modify long running Azure functions to send scan data to a webhook (rest endpoint) | DPI-76 | Subtask | Done | Palaniyappan Bala | 2024-03-07 03:29 | 2024-03-20 05:29 | 2024-04-03 06:31 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Create a web-hook endpoint to receive the results of the scan. | DPI-75 | Subtask | Done | Naveen Adusumilli | 2024-03-07 03:28 | 2024-03-20 05:29 | 2024-04-03 06:31 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Approval on the mouseflow javascript integration, that it doesn't add vulnerability to the application. | DPI-74 | Subtask | Done | V Thota | 2024-03-07 02:41 | 2024-04-03 00:26 | 2024-04-02 22:50 | DarkEye Performance
Integrating UBA scripts to frontend | DPI-73 | Subtask | Done | SaradhiMuneendra Gundabattina | 2024-03-07 02:41 | 2024-04-02 22:49 | 2024-04-03 06:31 | DarkEye Performance
Research on the User Behavior Analytics Products | DPI-72 | Subtask | Done | Manoj Singh Rawat | 2024-03-07 02:40 | 2024-03-26 04:52 | 2024-04-03 06:31 | DarkEye Performance
Zone Transfer Backend Integration | DPI-71 | Subtask | Not Required/Duplicate | Naveen Adusumilli | 2024-03-07 02:38 | 2024-03-27 06:00 | 2024-03-16 10:10 | DarkEye Performance
Zone Transfer UI design creation | DPI-70 | Subtask | Done | Ritika | 2024-03-07 02:37 | 2024-03-26 04:53 | 2024-04-03 06:31 | DarkEye Performance
Zone Transfer UI Development | DPI-69 | Subtask | Done | Sneha Sonyabapu Guthe | 2024-03-07 02:37 | 2024-04-02 02:53 | 2024-04-02 02:53 | DarkEye Performance
Reports Deployments | DPI-68 | Task | To Do | Naveen Adusumilli | 2024-03-06 01:39 | 2024-04-02 22:48 | 2024-03-26 04:57
User Behaviors Analytics Integration Deployment | DPI-67 | Task | Move To PROD | SaradhiMuneendra Gundabattina | 2024-03-06 01:39 | 2024-04-02 03:02 | 2024-04-03 00:26 | DarkEye Performance
Zone Transfer Script Deployment | DPI-65 | Task | Move To PROD | SaradhiMuneendra Gundabattina | 2024-03-06 01:38 | 2024-04-02 08:51 | 2024-04-02 22:49 | DarkEye Performance
Unable to Delete the Associated Vendor . | DPI-64 | Bug | To Do | Naveen Adusumilli | 2024-03-05 01:45 | 2024-03-18 08:06 | 2024-03-05 01:45
Self Assessment - All Domains - Need the validation for if the domain is already added in the DB then need to have the info message box. | DPI-50 | Bug | To Do | SaradhiMuneendra Gundabattina | 2024-02-28 01:37 | 2024-02-28 01:37 | 2024-04-03 06:31
All Domains - Pagination is not working in the Table. | DPI-49 | Bug | Done |  | 2024-02-27 06:29 | 2024-02-27 06:31 | 2024-04-03 06:31
Scan Notification trigger on new updates | DPI-48 | Story | Done | Kishore Aerravelly | 2024-02-22 02:48 | 2024-03-05 21:40 | 2024-03-05 20:56 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Allien Vault OTX integration with IOC | DPI-47 | Task | Done | Ajay Kumar Devarakonda | 2024-02-21 03:52 | 2024-03-05 21:40 | 2024-03-05 01:40 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Show scan in progress for breaches accordion and in card | DPI-45 | Task | Done | SaradhiMuneendra Gundabattina | 2024-02-20 04:39 | 2024-03-05 21:40 | 2024-03-05 02:08 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Update the email contents - use org name | DPI-44 | Task | Done | Manoj Singh Rawat | 2024-02-20 04:38 | 2024-03-05 21:40 | 2024-03-05 20:56 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Add logo to all email templates | DPI-43 | Task | Done | Manoj Singh Rawat | 2024-02-20 04:37 | 2024-03-05 21:40 | 2024-03-05 01:39 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Change color of Yara rule tab - yellow | DPI-42 | Task | Done | SaradhiMuneendra Gundabattina | 2024-02-20 04:35 | 2024-03-05 21:40 | 2024-03-05 01:39 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Verify date of vulnerability | DPI-41 | Bug | Done | Ajay Kumar Devarakonda | 2024-02-20 04:34 | 2024-03-05 21:40 | 2024-03-05 00:21 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Pagination - The serial number doesnt get set while navigating to other pages | DPI-39 | Bug | Done | SaradhiMuneendra Gundabattina | 2024-02-20 04:32 | 2024-03-20 11:10 | 2024-03-20 11:09
Sort Actively Exploited Vulnerabilities by number of attacks. | DPI-37 | Task | Done | Naveen Adusumilli | 2024-02-19 07:45 | 2024-03-05 21:40 | 2024-03-05 01:36 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Threat Prism - Pagination problem, when moving to next pages, serial number doesn't get reset. | DPI-36 | Bug | Done | SaradhiMuneendra Gundabattina | 2024-02-19 07:44 | 2024-03-05 21:40 | 2024-03-05 04:04 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Threat Actor some dates are missing for the Last Updated Date. | DPI-35 | Bug | Done | Ajay Kumar Devarakonda | 2024-02-19 07:43 | 2024-03-20 03:12 | 2024-03-20 03:11 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Threat Prism renamed as the ThreatPrism | DPI-34 | Task | Done | SaradhiMuneendra Gundabattina | 2024-02-19 07:43 | 2024-03-05 21:40 | 2024-03-05 02:24 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Performance of loading of widgets in Darkeye . | DPI-33 | Bug | Done | Naveen Adusumilli | 2024-02-19 07:42 | 2024-03-20 03:29 | 2024-03-20 03:23 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
For the Huge Inventory Data the Cards are not showing the Update icon. | DPI-32 | Bug | Done | Amitabh Sharma | 2024-02-19 05:03 | 2024-03-20 04:21 | 2024-03-20 04:21 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Need Scan Completion email only when the entire Scan is completed. | DPI-31 | Task | Done | Manoj Singh Rawat | 2024-02-19 04:58 | 2024-03-20 05:27 | 2024-03-20 05:29 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Scan Logs - Selected Year - Add the Year 2024. | DPI-30 | Bug | Done | SaradhiMuneendra Gundabattina | 2024-02-19 04:32 | 2024-03-05 21:40 | 2024-03-05 01:33 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Self Assessment - All Domains - Unable to Scan all the domains At a time. | DPI-29 | Bug | Done | Naveen Adusumilli | 2024-02-18 22:53 | 2024-03-05 21:40 | 2024-03-05 03:23 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Scan Results are not populating same for the Breaches under the Different Org Details. | DPI-27 | Bug | To Do | Varad Balasaheb Bhalsing | 2024-02-18 22:48 | 2024-03-07 23:43 | 2024-03-07 09:07 | Darkeye Performance Enhancemen
Associate Domain - Unable to Add the Vendor. | DPI-26 | Bug | Done | SaradhiMuneendra Gundabattina | 2024-02-18 22:44 | 2024-03-05 21:40 | 2024-03-05 01:47 | Darkeye Performance Enhancemen | Darkeye Performance Enhancem
Paginations is not working. | DPI-25 | Bug | Done | Sneha Sonyabapu Guthe | 2024-02-18 22:42 | 2024-02-18 22:47 | 2024-04-03 06:31
Move the Scan Results from Third Party to Darkeyescan.com for the Primhealthcare Vendors. | DPI-24 | Task | Done | Naveen Adusumilli | 2024-02-18 22:42 | 2024-03-20 05:29 | 2024-03-20 05:27 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Need to manage the Login Session in same browser. (Improve) | DPI-23 | Task | Done | SaradhiMuneendra Gundabattina | 2024-02-15 21:38 | 2024-03-20 05:29 | 2024-03-20 05:27 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Threat Prism - Recently updated the Adversaries should be at the Top of the table. | DPI-22 | Bug | Done | Sneha Sonyabapu Guthe | 2024-02-15 21:38 | 2024-02-28 01:36 | 2024-04-03 06:31
Threat Prism - Hide the IOC which is having 0 IOC count. | DPI-20 | Bug | Done | Sneha Sonyabapu Guthe | 2024-02-15 21:37 | 2024-02-19 07:40 | 2024-04-03 06:31
Scan updates in DarkEye UI. | DPI-17 | Task | Done |  | 2024-02-15 04:45 | 2024-02-20 05:04 | 2024-04-03 06:31
Scan Updates Notification | DPI-16 | Task | Done |  | 2024-02-15 04:45 | 2024-02-22 03:19 | 2024-03-05 22:10
Email Notification Template - Customer User Onboarding. | DPI-15 | Bug | Done | Naveen Adusumilli | 2024-02-15 04:45 | 2024-03-20 04:19 | 2024-03-20 04:17 | Darkeye Performance Enhancemen | Darkeye Blocker Tasks
Send an email to the added Prime User's by Support Email ID. | DPI-14 | Task | Done |  | 2024-02-15 04:44 | 2024-02-15 04:44 | 2024-04-03 06:31
Added the List of Prime User to the Darkeye PROD. | DPI-13 | Task | Done |  | 2024-02-15 04:44 | 2024-02-15 04:44 | 2024-04-03 06:31
Report Testing. | DPI-12 | Task | Done | Sneha Sonyabapu Guthe | 2024-02-15 04:44 | 2024-02-27 09:47 | 2024-04-03 06:31
Breaches - Employee Leaks - Description - Need to remove the hyper link html tag. | DPI-11 | Task | Done | Sneha Sonyabapu Guthe | 2024-02-15 04:43 | 2024-02-19 07:39 | 2024-04-03 06:31
Prime healthcare (ECFirst) client mapped to darkeyescan.com (DE PROD) | DPI-10 | Task | Done |  | 2024-02-15 04:42 | 2024-02-15 04:42 | 2024-04-03 06:31
Vendor Assessment - Unable to add the Vendor. | DPI-9 | Bug | Done |  | 2024-02-15 04:41 | 2024-02-15 04:42 | 2024-04-03 06:31
Unable to see the left side navigation menu reported by Uma. | DPI-8 | Bug | Done |  | 2024-02-15 04:41 | 2024-02-15 04:41 | 2024-04-03 06:31
Have a loader /spinner Vendor assessment and dashboard while scanning. | DPI-7 | Task | Done |  | 2024-02-15 04:40 | 2024-02-15 04:40 | 2024-04-03 06:31
Sunset the ECFirst. | DPI-6 | Task | Done |  | 2024-02-15 04:40 | 2024-02-15 04:40 | 2024-04-03 06:31
Implementation of Key Cloak Forgot Password. | DPI-5 | Task | Done |  | 2024-02-15 04:39 | 2024-02-20 02:30 | 2024-04-03 06:31
Email Templates and Notifications | DPI-4 | Task | Done |  | 2024-02-15 04:34 | 2024-02-15 04:36 | 2024-04-03 06:31
Implement the Dehashed API. | DPI-3 | Task | Done |  | 2024-02-15 04:34 | 2024-02-15 04:34 | 2024-04-03 06:31
Add the SIG Questionnaires for the Client. | DPI-2 | Task | Done |  | 2024-02-15 04:33 | 2024-02-15 04:33 | 2024-04-03 06:31
SBOM- Unable to Scan the Repo. | DPI-1 | Bug | Move To PROD | Naveen Adusumilli | 2024-02-15 04:28 | 2024-03-26 01:13 | 2024-03-25 23:56 | Darkeye Performance Enhancemen | DarkEye Performance
% Total | 0% | 0% | 0% | 0% | 33.32% | 33.33% | 33.34% | 0% | 0%