## Loop Tasks
Tasks List | Resource Name | Date | Status
Create Designs for adding MITRE info for IOC Parser-Darkeye | Ritika Soni | 2024-05-03 | Done
Create Designs for SentiMind, displaying of multiple post | Suyash Neware | 2024-05-10 | Done
Create Designs for SentiMind, displaying of multiple post | Shrashti Singhal | 2024-05-10 | Done
CI/CD Pipeline for bot application | Gopalswamy Ramalingam | 2024-05-09 | Done
CI/CD Pipeline for bot application | Sai | 2024-05-09 | Done
CI/CD Pipeline for bot application | Achyut Deshpande | 2024-05-09 | Done
AI Remediation Designs- Darkeye | Shrashti Singhal | 2024-05-09 | Done
AI Remediation Designs- Darkeye | Ritika Soni | 2024-05-09 | Done
April Sprint QA reported Bug fixes- UI | SaradhiMuneendra Gundabattina | 2024-05-02 | Done
April Sprint QA reported Bug fixes- UI | Mahesh Katti | 2024-05-02 | Done
April Sprint QA reported Bug fixes- Backend | Naveen Adusumilli | 2024-05-02 | Done
April Sprint QA reported Bug fixes- Backend | Amitabh Sharma | 2024-05-02 | Done
AI Remediation of Threats- Production Code, with config, Python Service/API | Somesh Fengade | 2024-05-17 | Move to Sprint
AI Remediation of Threats- Production Code, with config, Python Service/API | Jatin Singh | 2024-05-17 | Move to Sprint
AI Remediation of Threats- Production Code, with config, Python Service/API | Shashwat Srivastava | 2024-05-17 | Move to Sprint
Raise Ticket to Swimlane for script not running on upgraded version | Gopalswamy Ramalingam | 2024-05-02 | Done
Reports QA | Sneha Guthe | 2024-05-03 | Done
April Sprint QA | Sneha Guthe | 2024-05-03 | Done
Provide DevOps Tasks List for 2024 May | Gopalswamy Ramalingam | 2024-05-03 | Done
Conversion of 17 Azure functions to Fast API and add to Queue Manger, Plus Data Validation | Varad Bhalsing | 2024-05-16 | Blocked
Conversion of 17 Azure functions to Fast API and add to Queue Manger, Plus Data Validation | Ajay kumar | 2024-05-16 | Blocked
Sending a notification to User, in notification bell, when Bulk Uplois Done | Amitabh Sharma | 2024-05-07 | Move to Sprint
Scheduling Typo squatting of vendors to Swimlane--> Mimecast every day | Ajay kumar | 2024-05-10 | Hold
Completion of Scan Flag/ Endpoint when a Scan for one Domain gets Done. | Varad Bhalsing |  | Not Required
Completion of Scan Flag/ Endpoint when a Scan for one Domain gets Done. | Naveen Adusumilli |  | Not Required
Display of Scan completion in Notification Bell | Amitabh Sharma |  | Not Required
Create a Policy document for Darkeye using https://www.primehealthcare.com/policies/ https://www.privacypolicyonline.com/privacy-policy-generator/ | Pranav Sarda | 2024-05-03 | Move to Sprint
Adding & Scheduling Allien Vault IOCs to ThreatPrism- Darkeye, by addressing duplicates from Malpidea | Ajay kumar |  | Move to Sprint
2024 May Tasks Proposal- with the team | Shrashti Singhal | 2024-05-06 | Done
Research on sources for Remediation websites | Pranav Sarda |  | To do
Filtering of Alerts Code, deployment once received by Palan | Achyut Deshpande |  | Move to Sprint
Filtering of Alerts Code, deployment once received by Palan | Ajay kumar |  | Move to Sprint
Running the script for Swimlane for ~6K prime Vendors | Ajay kumar | 2024-06-07 | In Progress
Send April Resource Analytics Dashboard | Pranav Sarda | 2024-05-06 | Done
CI/CD for Harvard - Pulse | Achyut Deshpande | 2024-05-07 | Done
CI/CD for Harvard - Pulse | Gopalswamy Ramalingam | 2024-05-07 | Done
SSL deployment for Harvard | Achyut Deshpande |  | Done
SSL deployment for Harvard | Gopalswamy Ramalingam |  | Done
Offline deployment of Swimlane | Gopalswamy Ramalingam |  | To do
Release note for Darkeye | Pranav Sarda | 2024-05-13 | In Progress
Harvard Bug Fixes | Achyut Deshpande | 2024-05-14 | Move to Sprint
Harvard Bug Fixes | Naveen Adusumilli | 2024-05-14 | Move to Sprint
Logrthym and Prime follow up | Achyut Deshpande |  | To do
Validation on Bot Application thru CI/CD | Sai Sampath Chinthavatla | 2024-05-09 | Done
Validation on Bot Application thru CI/CD | Achyut Deshpande | 2024-05-09 | Done
Validation on Bot Application thru CI/CD | Sai Sampath Chinthavatla | 2024-05-09 | Done
Verify 'OR' 'AND' logic in filebeat | Achyut Deshpande | 2024-05-15 | Done
Take Dev Mongo DB creds/ as backup of Naveen for whitelisting | Gopalswamy Ramalingam | 2024-05-28 | To do
Bulk Uplonotification | Naveen Adusumilli | 2024-05-16 | To do
Bulk Uplonotification | Amitabh Sharma | 2024-05-16 | To do
Scan Manager darkeye, 2 tools debug and resolution | Varad Bhalsing | 2024-05-16 | Done
Scan Manager darkeye, 2 tools debug and resolution | Ajay kumar | 2024-05-16 | Done
Debug Inbound and Outbound Issue reported by Uma | Shrashti Singhal | 2024-05-14 | Done
Debug Inbound and Outbound Issue reported by Uma | Kishore Aerravelly | 2024-05-14 | Done
Debug Inbound and Outbound Issue reported by Uma | Manoj Singh | 2024-05-14 | Done
Update Filebeats with new Master Vlan sheet shared by Thota | Manoj Singh | 2024-05-14 | Done
Update Filebeats with new Master Vlan sheet shared by Thota | Sai Sampath Chinthavatla | 2024-05-14 | Done
Update Filebeats with new Master Vlan sheet shared by Thota | Achyut Deshpande | 2024-05-14 | Done
Give formatted list of Subnets to edit in FileBeat | Shrashti Singhal | 2024-05-14 | Done
Create Pulse- Harvard Credentials for Team | Ajay kumar | 2024-05-14 | Done
Verify Inbound Outbound data for devices- Pulse Prime( issue should resolve from 15th 2024 May, Changes wont be reflected on old dates) | Sneha Guthe | 2024-05-15 | On Hold
Harvard Deployment Testing | Sneha Guthe | 2024-05-16 | Done
SentiMind Enhancement Screens | Manoj Singh | 2024-05-24 | Part of Next Sprint
SentiMind Enhancement Screens | Mahesh Katti | 2024-05-24 | Part of Next Sprint
6th 2024 2024 May 10th 2024 May deployment testing and sign off | Sneha Guthe | 2024-05-24 | Done
Help Sneha in logging in Harvard Environment | Achyut Deshpande | 2024-05-15 | To do
Help Sneha in logging in Harvard Environment | MS Manoj Singh | 2024-05-15 | To do
Look into session management requirement given by Thota | Ajay kumar | 2024-05-29 | To do
Look into session management requirement given by Thota | SaradhiMuneendra Gundabattina | 2024-05-29 | To do
Schedule Alerts signature for Pulse/ Reaearch on Suricata to take rules | Ajay kumar | 2024-05-24 | Done
Unified Pulse Code replacement to Prime and AVH. (to be planned after Harvard testing and signoff) | Gopalswamy Ramalingam | 2024-05-21 | In Progress
Unified Pulse Code replacement to Prime and AVH. (to be planned after Harvard testing and signoff) | Achyut Deshpande | 2024-05-21 | In Progress
Unified Pulse Code replacement to Prime and AVH. (to be planned after Harvard testing and signoff) | Naveen Adusumilli | 2024-05-21 | In Progress
Unified Pulse Code replacement to Prime and AVH. (to be planned after Harvard testing and signoff) | Ajay kumar | 2024-05-21 | In Progress
Post resource utilization graph of all 3 Pulse Environments on the group | Sai Sampath Chinthavatla | 2024-05-15 | To do
Create Darkeye Release Notes | Pranav Sarda | 2024-05-16 | To do
Create Darkeye Release Notes | Shrashti Singhal | 2024-05-16 | To do
Deploy Alerts Filtering Code by Palan on Pulse | Ajay kumar | 2024-05-22 | To do
Deploy Alerts Filtering Code by Palan on Pulse | Gopalswamy Ramalingam | 2024-05-22 | To do
Offline Swimlane deployment | Thota | 2024-05-22 | In Review
Designs for IOC - Parser Threat Prism | Ritika Soni | 2024-05-17 | Done
Users not able able to login in AVH - ad accounts | Ajay kumar | 2024-05-13 | To do
Post Omnicell Analysis asked by Thota | Naveen Adusumilli | 2024-05-15 | To do
DataCenters sensors status | Achyut Deshpande | 2024-05-13 | To do
Research on Alerting on resources Threshold for Pulse | Sai Sampath Chinthavatla | 2024-05-28 | In Progress
Research on Alerting on resources Threshold for Pulse | Gopalswamy Ramalingam | 2024-05-28 | In Progress
Change file beat for all logs, add subnets-Testing Pending | Sneha Guthe |  | On Hold
Onboard LPIH Sensor | Gopalswamy Ramalingam | 2024-05-21 | Done
Email Uma with status on 48 sensors, for any kind of issue | Sai Sampath Chinthavatla |  | To do
Email Uma with status on 48 sensors, for any kind of issue | Achyut Deshpande |  | To do
Snort Bot Diagnosis | Ajay kumar |  | On Hold
Snort Bot Diagnosis | Naveen Adusumilli |  | On Hold
Snort Bot Diagnosis | Manoj Singh |  | On Hold
Ask Pulse deployment on AVH | Achyut Deshpande | 2024-05-28 | To do
Ask Pulse deployment on AVH | Ajay kumar | 2024-05-28 | To do
Ask Pulse deployment on AVH | Gopalswamy Ramalingam | 2024-05-28 | To do
Configurations on server and sensors, disk space alerts on 80% AVH | Sai Sampath Chinthavatla |  | To do
Configurations on server and sensors, disk space alerts on 80% Harvard | Sai Sampath Chinthavatla |  | To do
Configurations on server and sensors, disk space alerts on 80% Harvard | Achyut Deshpande |  | To do
Post on group on Cassandra Data settings (days of data saved on AVH, Harvard, Prime) | Naveen Adusumilli | 2024-05-22 | To do
log4j Report- version details | Naveen Adusumilli |  | To do
log4j Report- version details | Gopalswamy Ramalingam |  | To do
Send instructions tograj on login in using console cable | Gopalswamy Ramalingam |  | Done
List down tasks undertaken in Session management of Pulse | SaradhiMuneendra Gundabattina |  | To do
List down tasks undertaken in Session management of Pulse | Shrashti Singhal |  | To do
List down tasks undertaken in Session management of Pulse | Ajay kumar |  | To do
Send write up for Log4J to Thota | Kishore Aerravelly |  | To do
increase time out nginx | Gopalswamy Ramalingam | 2024-05-22 | Done
Get the list of Active sensors @ Prime | Sai Sampath Chinthavatla | 2024-05-24 | To do
Testing of Alerts at prime env | Manoj Singh | 2024-05-24 | To do
NVNV sensor, check suricata filters, latest rules are not getting picked | Achyut Deshpande | 2024-05-24 | To do
Configurations on server and sensors, disk space alerts on 80% Prime | Achyut Deshpande |  | To do
Configurations on server and sensors, disk space alerts on 80% Prime | Sai Sampath Chinthavatla |  | To do
Delete counter tables data older than 3 months AVH, Harvard, Prime | Naveen Adusumilli | 2024-05-28 | To do
Delete counter tables data older than 3 months AVH, Harvard, Prime | Achyut Deshpande | 2024-05-28 | To do
Delete counter tables data older than 3 months AVH, Harvard, Prime | Manoj Singh | 2024-05-28 | To do
Validate the Other Projects Tickets in the JIRA. | Sneha Guthe | 2024-05-24 | To do
Delete work/Spark directories on AVH, Harvard, Prime | Achyut Deshpande | 2024-05-27 | Done
Set up new MYSQL on Prime | Naveen Adusumilli | 2024-05-24 | Done
Set up new MYSQL on Prime | Achyut Deshpande | 2024-05-24 | Done
Configurations on server and sensors, disk space alerts on 80% Prime | Achyut Deshpande | 2024-05-28 | To do
Configurations on server and sensors, disk space alerts on 80% Prime | Sai Sampath Chinthavatla | 2024-05-28 | To do
Diagnose AVH Kafka Feed ( refer monitoring Screenshot) | Sai Sampath Chinthavatla |  | Done
Diagnose AVH Kafka Feed ( refer monitoring Screenshot) | Achyut Deshpande |  | Done
Mount radio folder- Pulse Prime | Achyut Deshpande
Mount radio folder- Pulse Prime | Naveen Adusumilli
Onboard Prime Users | Ajay kumar | 2024-05-24
Ask Pulse deployment on AVH | Ajay kumar | 2024-05-28 | In Progress
Ask Pulse deployment on AVH | Achyut Deshpande | 2024-05-28 | In Progress
Deploy Alerts filtering code on AVH | Ajay kumar | 2024-05-24 | In Progress
Deploy Alerts filtering code on AVH | Achyut Deshpande | 2024-05-24 | In Progress
Take Dev Mongo DB creds/ as backup of Naveen for whitelisting- add support@culinda.com email address | Gopalswamy Ramalingam | 2024-05-28 | To do
Swimlane Trellix and Logarithm integration- course/study material | Gopalswamy Ramalingam
Ci/CD pipeline for Darkeye Prod API server | Gopalswamy Ramalingam
Research on Alerting on resources Threshold for Pulse | Achyut Deshpande | 2024-05-28
Research on Alerting on resources Threshold for Pulse | Gopalswamy Ramalingam | 2024-05-28
Offline Swimlane deployment- Testing Pending by Thota | Gopalswamy Ramalingam | 2024-05-22 | In Review
Offline Swimlane deployment- Testing Pending by Thota | Thota | 2024-05-22 | In Review
SentiMind Enhancement Screens | Mahesh Katti | 2024-05-29 | Done
SentiMind Enhancement Screens | Manoj Singh | 2024-05-29 | Done
Testing of Alerts at prime env | Manoj Singh | 2024-05-27 | Done
Delete counter tables data older than 3 months AVH, | Achyut Deshpande | 2024-05-28 | Done
Delete counter tables data older than 3 months AVH, | Naveen Adusumilli | 2024-05-28 | Done
Delete counter tables data older than 3 months AVH, | Manoj Singh | 2024-05-28 | Done
Prime Inventory restoration | Naveen Adusumilli
Snort Bot Diagnosis Prime | Naveen Adusumilli | 2024-05-31 | In Progress
Delete Nov counter tables Prime Pulse | Naveen Adusumilli | 2024-05-24
Delete Nov counter tables Prime Pulse | Manoj Singh | 2024-05-24
Check Rapid 7- Pulse AVH( no Data) | Naveen Adusumilli
Check Rapid 7- Pulse AVH( no Data) | Sneha Guthe
Delete counter tables data older than 3 months Harvard, Prime | Naveen Adusumilli
Check Tenable - Pulse Prime ( no data) | Naveen Adusumilli
Add 4 more requirements given by Thota to Session Management | Ajay kumar | 2024-05-29 | Done
Add 4 more requirements given by Thota to Session Management | SaradhiMuneendra Gundabattina | 2024-05-29 | Done
6th 2024 2024 May 10th 2024 May deployment testing and closing the Sprint on Jira | Sneha Guthe | 2024-05-28 | Done
Verify Inbound Outbound data for devices- Pulse Prime( issue should resolve from 15th 2024 May, Changes wont be reflected on old dates) ON HOLD as Pulse Prime UI is inaccessible | Sneha Guthe | 2024-05-15 | On Hold
Change file beat for all logs, add subnets-Testing Pending | Sneha Guthe |  | On Hold
Test AVH ENV | Sneha Guthe | 2024-05-24 | Done
Running the script for Swimlane for ~6K prime Vendors, The script is running from 3 weeks. 1 more week to go for 1 time addition of domain squatting for Prime Vendors | Varad Bhalsing | 2024-06-03
Schedule Swimlance- Mimecast Script (after one time run) ON HOLD | Varad Bhalsing | 2024-06-04
21st 2024 2024 May 28th 2024 May deployment testing on QA Environment (Darkeye) | Sneha Guthe | 2024-06-03 | In Progress
AVH 11 devices only | Naveen Adusumilli
IOE Risk in AVH | Ajay kumar
IOE Risk in AVH | Shrashti Singhal
IOE Risk in Prime | Ajay kumar
Alerts AVH no data | Ajay kumar
New design development for IOE Vulnerability | Ritika Soni
New design development for IOE Vulnerability | Shrashti Singhal

## Sprint Tasks
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Updated | Sprint
Task | PPI-111 | 14511 | Load Data in dev for Testing | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-27 22:47 | Pulse UI Issues
Task | PPI-108 | 14502 | Auto Deletion of Spark logs Prime | Sai Sampath Chinthavatla | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 04:01 | Pulse UI Issues
Task | PPI-107 | 14501 | Auto Deletion of Spark Logs in AVH | Sai Sampath Chinthavatla | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:27 | Pulse UI Issues
Task | PPI-106 | 14500 | Auto Deletion of Spark Logs in harvard | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:26 | Pulse UI Issues
Task | PPI-105 | 14499 | AVH Deployment of Pulse by Using new Pulse(unified)branch | Gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:25 | Pulse UI Issues
Task | PPI-103 | 14497 | Storage Alerts on AVH | Sai Sampath Chinthavatla | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:22 | Pulse UI Issues
Task | PPI-102 | 14496 | Storage alerts on Harvard | Sai Sampath Chinthavatla | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:22 | Pulse UI Issues
Task | PPI-101 | 14495 | Harvard Pulse deployment | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:22 | Pulse UI Issues
Task | PPI-100 | 14494 | Auto CI CD Pulse deployment Pipeline | Gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:04 | Pulse UI Issues
Task | PPI-99 | 14493 | deployment of Unified Pulse Branch to Pulse Dev | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:03 | Pulse UI Issues
Task | PPI-98 | 14492 | Single Unified Pulse Branch Creation | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-27 03:02 | Pulse UI Issues
Task | PPI-97 | 14487 | Swimlane offline Deployment | V Thota | 5d7508ca8ce6b60c38109fd3 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23 06:25 | Pulse UI Issues
Task | PPI-96 | 14486 | Replacement of Subnets on Filebeats- Prime | Sai Sampath Chinthavatla | 641d1fd01273131f2ae2a16f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23 06:24 | Pulse UI Issues
Subtask | PPI-92 | 14481 | Message on old session that user is kicked out because of new session | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | In Progress | 2024-05-23 02:54 | Pulse UI Issues
Subtask | PPI-91 | 14480 | Add a error message on loged out session | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | In Progress | 2024-05-23 02:53 | Pulse UI Issues
Bug | PPI-90 | 14479 | Ask Pulse isn't working in dev | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23 02:11 | Pulse UI Issues
Bug | PPI-89 | 14478 | Asset Inventory- Individual Devices- Change the placement of dollor sign( in front of the value) | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23 02:08 | Pulse UI Issues
Bug | PPI-88 | 14477 | Asset Inventory- GRID VIEW- Add Likelihood of Loss(use the fix from Demo) | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23 02:06 | Pulse UI Issues
Bug | PPI-87 | 14476 | Asset Inventory- GRID VIEW- Add risk( use the fix from Demo) | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-23 02:06 | Pulse UI Issues
Bug | PPI-86 | 14475 | Asset Inventory- GRID View- Online device not working(use the fix from demo) | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | To Do | 2024-05-23 02:04 | Pulse UI Issues
Subtask | PPI-85 | 14474 | Session management when same user switch from one IP to other | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | In Progress | 2024-05-22 07:44 | Pulse UI Issues
Subtask | PPI-84 | 14473 | Add timer for inactive sessions | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | In Progress | 2024-05-22 07:43 | Pulse UI Issues
Task | PPI-83 | 14472 | Session Management | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22 07:43 | Pulse UI Issues
Task | PPI-82 | 14471 | Ask Pulse as a deployable module for devops on every new installation | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22 04:06 | Pulse UI Issues
Task | PPI-81 | 14470 | Auto Alerts Filter on Pulse (python Code) | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-05-22 04:06 | Pulse UI Issues
Bug | PPI-60 | 14249 | Dashboard- Merge 2nd and 4th Widget | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | QA | 2024-03-09 22:19 | Pulse UI Issues
Bug | PPI-54 | 14197 | Risk Lens – IOE Risk – Global Filter is not resetting the Widget Data. | Sneha Guthe | 625f945860d67c0068d8956f | Sneha Guthe | 625f945860d67c0068d8956f | Medium | QA | 2024-03-01 08:23 | Pulse UI Issues
Bug | PPI-42 | 14185 | Investigation – Managed & Unmanaged Devices – View All Filter is not working properly. (In the View All We Need Data in Table View) | Sneha Guthe | 625f945860d67c0068d8956f | Sneha Guthe | 625f945860d67c0068d8956f | Medium | QA | 2024-03-01 08:17 | Pulse UI Issues
Bug | PPI-41 | 14184 | Revenue Dormant Devices – No of Device count should have to increase (Y Axis) As Graph Bar values going more than that. | Sneha Guthe | 625f945860d67c0068d8956f | Sneha Guthe | 625f945860d67c0068d8956f | Medium | QA | 2024-03-01 08:15 | Pulse UI Issues
Bug | PPI-40 | 14183 | Device Risk Comparison Widget is not working properly.- Use the fix from Demo | Sneha Guthe | 625f945860d67c0068d8956f | Sneha Guthe | 625f945860d67c0068d8956f | Medium | QA | 2024-03-01 08:14 | Pulse UI Issues
Task | PPI-29 | 14168 | Need to Show Table View If the Records are greater than 10 under the Inbound & Outbound. | Sneha Guthe | 625f945860d67c0068d8956f | Sneha Guthe | 625f945860d67c0068d8956f | Medium | QA | 2024-02-20 09:27 | Pulse UI Issues
Bug | DPI-307 | 14512 | CM is not getting enabled under the Other Org (Prime Health Care). | Sneha Guthe | 625f945860d67c0068d8956f | Sneha Guthe | 625f945860d67c0068d8956f | Medium | Done | 2024-05-28 01:30 | SentiMind & Bug Fixes
Task | DPI-300 | 14491 | Add a counter for posts in Instagram to create Unique IDs | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-25 03:13 | SentiMind & Bug Fixes
Task | DPI-296 | 14482 | SentiMind- Post Filter | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-23 04:52 | SentiMind & Bug Fixes
Subtask | DPI-281 | 14455 | UI Services Integration | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:37 | SentiMind & Bug Fixes
Subtask | DPI-280 | 14454 | Mongo DB Queries and Java Services | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:36 | SentiMind & Bug Fixes
Subtask | DPI-279 | 14453 | Create UI | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:36 | SentiMind & Bug Fixes
Task | DPI-278 | 14452 | SentiMind- On Clicking posts, fetch comments on the posts | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:36 | SentiMind & Bug Fixes
Subtask | DPI-277 | 14451 | Integration of UI and Services | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:34 | SentiMind & Bug Fixes
Subtask | DPI-276 | 14450 | Java Service and Mongo DB queries | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:30 | SentiMind & Bug Fixes
Subtask | DPI-275 | 14449 | Create UI | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:30 | SentiMind & Bug Fixes
Task | DPI-274 | 14448 | SentiMind- Show post in main page instead of Comments | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:30 | SentiMind & Bug Fixes
Subtask | DPI-273 | 14447 | Java Service and Mongo DB query | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:26 | SentiMind & Bug Fixes
Task | DPI-272 | 14446 | SentiMind- Fetching posts/comments per author | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:25 | SentiMind & Bug Fixes
Subtask | DPI-271 | 14445 | UI service integration | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:24 | SentiMind & Bug Fixes
Subtask | DPI-270 | 14444 | UI developemnt | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:24 | SentiMind & Bug Fixes
Subtask | DPI-269 | 14443 | Java Service and Mongo DB query | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:21 | SentiMind & Bug Fixes
Task | DPI-268 | 14442 | SentiMind- Sentiment Trend | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:21 | SentiMind & Bug Fixes
Subtask | DPI-267 | 14441 | UI and Service Integration | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:20 | SentiMind & Bug Fixes
Subtask | DPI-266 | 14440 | Design Development | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:19 | SentiMind & Bug Fixes
Subtask | DPI-265 | 14439 | Java Services | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:17 | SentiMind & Bug Fixes
Task | DPI-264 | 14438 | SentiMind- Engagement Trendline Drilldown | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:17 | SentiMind & Bug Fixes
Task | DPI-263 | 14437 | SentiMind- Navigate to Authors on Clicking on Positive or Negative Authors on the card View | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-22 03:16 | SentiMind & Bug Fixes
Bug | DPI-225 | 14399 | Multiple completion notification for single scan | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-21 23:01 | SentiMind & Bug Fixes
Bug | DPI-224 | 14398 | Continuous monitoring doesn't show disabled icon, once end date is crossed | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-20 07:57 | DarkEye Bulk Automation 2
Bug | DPI-223 | 14397 | Continuous monitoring is enabled for previous Dates | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-20 07:55 | DarkEye Bulk Automation 2
Bug | DPI-222 | 14395 | Sentimind- Score overflow | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-10 06:22 | DarkEye Bulk Automation 2
Bug | DPI-220 | 14393 | Spelling correction- Vendor Profile | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-09 07:02 | DarkEye Bulk Automation 2
Bug | DPI-219 | 14392 | Empty word Cloud | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-09 07:00 | DarkEye Bulk Automation 2
Bug | DPI-218 | 14391 | Negative comments in Prime environment. | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Not Required/Duplicate | 2024-05-08 23:00 | DarkEye Bulk Automation 2
Bug | DPI-217 | 14390 | Today Sentiment- SentiMind | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-07 04:50 | DarkEye Bulk Automation 2
Task | DPI-216 | 14389 | Schedule Alien Valut | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-06 03:37 | DarkEye Bulk Automation 2
Subtask | DPI-215 | 14388 | Count of engagements donot match on card and individual website for today | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Not Required/Duplicate | 2024-05-05 12:39 | DarkEye Bulk Automation 2
Bug | DPI-214 | 14387 | Bug Fixes in SentiMind | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Not Required/Duplicate | 2024-05-05 12:38 | DarkEye Bulk Automation 2
Task | DPI-213 | 14386 | Reports Endpoint change | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:37 | DarkEye Bulk Automation 2
Subtask | DPI-205 | 14378 | Integrating end point with Notification Bell Icon | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:33 | DarkEye Bulk Automation 2
Subtask | DPI-204 | 14377 | Java service to download paginated table | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:33 | DarkEye Bulk Automation 2
Task | DPI-203 | 14376 | Bulk Upload completion notification for each domain | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:32 | DarkEye Bulk Automation 2
Task | DPI-202 | 14375 | Download Option for adversaries- IOC parser Threat Prism | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:31 | DarkEye Bulk Automation 2
Subtask | DPI-201 | 14374 | Add bulk monitoring to bulk upload check box | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:30 | DarkEye Bulk Automation 2
Subtask | DPI-200 | 14373 | Bulk Monitoring end point | Amitabh Sharma | 712020:c4cfd63f-7065-4992-8dea-faf82f25458a | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:30 | DarkEye Bulk Automation 2
Subtask | DPI-199 | 14372 | Enable it in front end | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:29 | DarkEye Bulk Automation 2
Subtask | DPI-198 | 14371 | Create a service to enable continuous Monitoring in Bulk | Manoj Singh | 60a230f15998a60068436f2b | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:29 | DarkEye Bulk Automation 2
Task | DPI-197 | 14370 | Add continuous monitoring to bulk Upload | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:29 | DarkEye Bulk Automation 2
Task | DPI-196 | 14369 | Add continuous monitoring to Bulk Actions | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:28 | DarkEye Bulk Automation 2
Task | DPI-195 | 14368 | Scan Tools Enhancement | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-05 12:25 | DarkEye Bulk Automation 2
Bug | DPI-194 | 14367 | Formula to calculate Sentiment score incorrectly implemented For comments For Posts | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-03 09:56 | DarkEye Bulk Automation
Bug | DPI-193 | 14366 | Pie charts should be percentage- it was numbers. Changed to %ages Global For Comments For Posts | Sneha Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 60ba18cb66df7900708f9114 | Medium | Done | 2024-05-03 09:56 | DarkEye Bulk Automation