## Sprint Tasks
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Priority | Assignee | Assignee Id | Creator | Date
deployment of scan manager code on QA, which was on dev servers | DPI-860 | 15130 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | gopal | 63b3b9f8b790087ed71179a2 | Sneha Sonyabapu Guthe | 2024-11-29 06:50
Change of refresh token for scan manager tool execution status | DPI-859 | 15129 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Sneha Sonyabapu Guthe | 2024-11-29 06:41
Vendor: Answering Form- Multiple people can answer and save draft, next user will see it from there | DPI-858 | 15128 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-29 00:05
Vendor: Pending Questionnaire- Add Status Column | DPI-857 | 15127 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-29 00:05
Add fields in forms | DPI-856 | 15126 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-26 01:44
Add HIdden fields dynamically vis API | DPI-855 | 15125 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-26 01:43
Client- Sent Questionnaire- Sent to Column should see new POC added by Vendor | DPI-852 | 15122 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-29 00:05
Client- Received Questionnaire- Rename Asignee | DPI-851 | 15121 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-28 00:09
Vendor: In Progress Questionnaire- Add Score Column | DPI-850 | 15120 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:26
Pop at the submittion about number of apporved/ disapproved or the form has been approved and updates are sent to the vendor | DPI-849 | 15119 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:13
Client should be able to see status of each question as approved or disapproved | DPI-848 | 15118 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:13
Client should be able approve or add notes to previously disapprove questions | DPI-847 | 15117 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:12
Client shouldnt be able to re review the approved answers ( only able to see) | DPI-846 | 15116 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:12
On Submitting, Review- CLient should see score in pop up that( 7/10 questions are approbed and 3/10 questionns are sent to rework to Vendor) | DPI-845 | 15115 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:11
Vendor should be able to see score on top of answer sheet (4/10) as approved | DPI-844 | 15114 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:09
Vendor shouldn't be able to change approved questions, should be locked | DPI-843 | 15113 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:08
Vendor should be able to see the status & Notes of each question | DPI-842 | 15112 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:08
Vendor- Rework | DPI-841 | 15111 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:26
Client- Re- Reviewing Form | DPI-840 | 15110 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:26
Client should be able to approve, disapprove, and add note to each answer | DPI-839 | 15109 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:04
CLient should not be allowed to change answers, Answers should be locked | DPI-838 | 15108 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:04
Client can assign to someone else ( add POC from User Management) | DPI-837 | 15107 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:03
No need to assign it to me(by default it should be assigned to the person who sent it) | DPI-836 | 15106 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 03:02
Client- Reviewing Form | DPI-835 | 15105 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:26
Client- Received Questionnaire- Assignee | DPI-834 | 15104 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:26
Cleint: Received Questionnaire- Rename Tab( Action Items) | DPI-833 | 15103 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-28 00:45
When a form is send to rework | DPI-832 | 15102 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-25 02:14
When a form is approved | DPI-831 | 15101 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 02:56
When Client sends a form to Vendor | DPI-830 | 15100 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 02:55
Email Notifications from Client to Vendor | DPI-829 | 15099 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:25
When a Vendor Submits/Resubmits a form | DPI-828 | 15098 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 02:54
When Vendor assigns to it a POC not listed by Client Initially | DPI-827 | 15097 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-22 02:54
Email Notification from Vendor TO Client | DPI-826 | 15096 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:25
Vendor: Answering Form- Assign to another POC or add POC | DPI-825 | 15095 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:25
Vendor: Answering Form- Comments | DPI-824 | 15094 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-26 22:42
Vendor: Answering Form- Assign to Myself | DPI-823 | 15093 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-27 21:19
Client: Send Questionnaire- Types of Status | DPI-822 | 15092 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-27 21:18
Client: Send Questionnaire- Rename to (All Questionnaire) | DPI-821 | 15091 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-27 21:18
Vendor: In Progress Questionnaire- Add Status Column | DPI-820 | 15090 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-26 22:39
Client: Send Questionnaire- Add Vendor POC Default POC | DPI-819 | 15089 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-27 21:18
Create Forms | DPI-818 | 15088 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-22 03:27
UI bulk Email | DPI-793 | 15063 | Subtask | Has Blocker | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-26 00:54
Python code update | DPI-773 | 15043 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-14 02:10
RSS Feed update | DPI-772 | 15042 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-11-10 22:33
Take down domain: Abuse email address missing | DPI-771 | 15041 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-15 05:38
Credits, Pricing and Subscription Module | DPI-764 | 15034 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-08 02:45
Reminders and Snooze | DPI-763 | 15033 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-16 09:29
Alerting Module: Add alerts to Threats, Breaches etc. | DPI-762 | 15032 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-16 09:29
Vendor Ratings | DPI-761 | 15031 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-11-08 02:42
BotNet: Monitor IP addresses- RnD | DPI-760 | 15030 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-11-08 02:38
NewsFeed: Recorded Future Bug | DPI-756 | 15026 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-11-15 05:47
Optimize Emerging Threats News Feed Code | DPI-755 | 15025 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-15 05:25
Rapid7 | DPI-754 | 15024 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-15 06:07
Logrthym | DPI-753 | 15023 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-15 06:03
Tenable | DPI-752 | 15022 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-15 06:06
Mimecast | DPI-751 | 15021 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-15 06:03
Research on Tines- RnD | DPI-750 | 15020 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-15 06:07
Services for informing about backend scan job | DPI-749 | 15019 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-05 01:06
New Column in UI | DPI-748 | 15018 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-15 03:48
New column in code after scheduler run | DPI-747 | 15017 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 2024-11-15 03:48
ThreatPrism: ThreatPrism update date | DPI-746 | 15016 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 2024-11-15 03:48
Sentry Production issues in Rest Services | DPI-745 | 15015 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-14 02:15
Report UI mismatch Report | DPI-742 | 15012 | Story | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 2024-11-24 22:07
Wait game: Loader Game | DPI-733 | 15003 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-10 02:32
Intel Vault: Assign Categories if empty for Threat Adversaries | DPI-732 | 15002 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-15 05:33
Adversary Category Mapping | DPI-730 | 15000 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-07 04:01
IOC category Mapping | DPI-729 | 14999 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-07 02:10
Mapping of IOC categories and Adversary Categories | DPI-728 | 14998 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-07 02:09
Fill in data for old adversary Names | DPI-718 | 14988 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-06 03:55
Add 2 fields for Adversary- Objective & Technical Details | DPI-717 | 14987 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-06 03:54
Add 2 columns in UI for Objective & Technical details in 2nd part of the table. | DPI-716 | 14986 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-06 03:54
Update Objective & Technical Details of Adversaries In Threat Prism / Intel Vault | DPI-715 | 14985 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-06 03:56
get service to fetch Analysts names | DPI-714 | 14984 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-11-06 00:10
Remove Beta tags | DPI-710 | 14980 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-06 00:10
UI for 708 | DPI-709 | 14979 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-06 20:57
First item to look different(as not clickable) | DPI-708 | 14978 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ritika | 712020:2d9accdf-0317-4bb6-bb87-b5fb4b160527 | Shrashti Singhal | 2024-11-06 20:57
Hover highlighting on bottom 3 items | DPI-707 | 14977 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-06 20:57
Account Menu Enhancement | DPI-706 | 14976 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-05 23:31
Sentry Issues in SBOM- Vulnerability & components not loading | DPI-705 | 14975 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-06 20:42
CourtCase Integration - RnD | DPI-700 | 14960 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-11-12 13:06
UI | DPI-698 | 14958 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-06 00:10
Post service | DPI-697 | 14957 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-11-06 00:10
Intel Vault - Analyst Name to editable when None | DPI-696 | 14956 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-11-06 00:10
Services | DPI-695 | 14955 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-06 00:08
UI | DPI-694 | 14954 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-06 00:08
Intel Vault - IOC Category, Adversary Category & Status to be multiple select (check Boxes instead of drowpdowns) | DPI-693 | 14953 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-06 00:07
Intel Vault & threatPrism Scheduler in CI CD | DPI-692 | 14952 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 2024-11-29 06:50
Services | DPI-691 | 14951 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-11-05 23:50
UI | DPI-690 | 14950 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-05 23:50
Intel Vault - Drop down along with Search on Adversary Names | DPI-689 | 14949 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-05 23:50
Change the threatPrism code to remove categories in Intel Valut | DPI-688 | 14948 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-07 02:02
Remove data from database from other categories | DPI-687 | 14947 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-07 02:02
Intel Vault - remove of IOCs of extra categories | DPI-686 | 14946 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-07 02:02
Database data correction | DPI-685 | 14945 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-11-05 23:38
UI correction on table dropdown, add & edit | DPI-684 | 14944 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-05 23:38
Intel Vault - Disseminated Spelling Correction | DPI-683 | 14943 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-05 23:38
Database storage if needed | DPI-682 | 14942 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-07 04:02
Backend Integration with UI | DPI-681 | 14941 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-05 23:05
Integrate with Existing News Feed & scheduling | DPI-680 | 14940 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Shashwat Srivastava | 712020:bd17afcc-3aa8-42a7-be71-f016500a225e | Shrashti Singhal | 2024-11-07 04:02
Python Code to fetch Feeds | DPI-679 | 14939 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Shashwat Srivastava | 712020:bd17afcc-3aa8-42a7-be71-f016500a225e | Shrashti Singhal | 2024-11-05 23:05
RSS feed/ API snippet | DPI-678 | 14938 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-11-05 23:05
UI- Addition of Emerging Threats and drown down list of 7 Feed | DPI-677 | 14937 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-11-07 04:02
News Feed - Add Emerging Threats | DPI-676 | 14936 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-05 23:05
LegalLens: CourtCases related to Domains, CEOS, keywords | DPI-675 | 14935 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-04 21:42
Typo-Squatting Data Mismatch in UI & Report. | DPI-674 | 14934 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Sneha Sonyabapu Guthe | 2024-11-06 22:47
News Feed- special characters present in the names of the News Feed catalogue | DPI-671 | 14930 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-06 03:59
Website tech stack replace Criminal IQ API to inhouse code- RnD | DPI-579 | 14835 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-11-18 23:47
RiskCraft: Threat Modelling Utility in Darkeye | DPI-553 | 14808 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Somesh Fengade | 712020:8e75e228-f554-4396-9a80-82361f5f4833 | Shrashti Singhal | 2024-11-04 21:42
Darkeye Release Notes | DPI-394 | 14630 | Story | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Pranav Ramchandra Sarda | 712020:144587d8-c7bc-4fd5-9248-7250dcb11783 | Shrashti Singhal | 2024-11-04 21:50
Infrastructure BenchMarking Darkeye | DPI-381 | 14617 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 2024-11-07 04:01
NightHawk: beta-RnD DarkeyeChatbot | DPI-324 | 14537 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Somesh Fengade | 712020:8e75e228-f554-4396-9a80-82361f5f4833 | Shrashti Singhal | 2024-11-04 21:42
Take Down Domain- Reporting email ID isn't avaiable | DPI-232 | 14406 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-11-11 01:00
Develop Forms | DPI-158 | 14330 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-06 05:47
Form AI: Develop forms | DPI-155 | 14327 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-11-08 02:33