## Sprint Tasks
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Priority | Assignee | Assignee Id | Creator | Date
Forms Flow Test Report | DPI-743 | 15013 | Story | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 2024-10-28 05:48
History Report | DPI-741 | 15011 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-28 05:46
UI integration | DPI-740 | 15010 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-28 05:44
Report | DPI-739 | 15009 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-28 05:45
Docker | DPI-738 | 15008 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-28 05:45
Python code | DPI-737 | 15007 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-28 05:45
API Snippet | DPI-736 | 15006 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rohan Kaushik | 712020:7d5564a1-1031-4966-88bb-e1d23911ea8d | Shrashti Singhal | 2024-10-29 00:32
UI development | DPI-735 | 15005 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-28 05:45
Design | DPI-734 | 15004 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ritika | 712020:2d9accdf-0317-4bb6-bb87-b5fb4b160527 | Shrashti Singhal | 2024-10-28 05:45
Add keyword, domains name etc as suggestion for Sentimind- suggested by Uma | DPI-726 | 14996 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-10-22 23:39
Integrate K6 Commands on Dashboard | DPI-725 | 14995 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 2024-10-22 23:37
Test K6 Commands in isloation(local) | DPI-724 | 14994 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Sneha Sonyabapu Guthe | 625f945860d67c0068d8956f | Shrashti Singhal | 2024-10-22 23:36
setup Prometheus on Azure | DPI-723 | 14993 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 2024-10-22 23:36
Setup Grafana Dashboard on Azure | DPI-722 | 14992 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 2024-10-22 23:36
setup k6 on Azure | DPI-721 | 14991 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Achyut Deshpande | 611b662b41ff95006a7dd993 | Shrashti Singhal | 2024-10-22 23:36
C/CD for Sentimind | DPI-719 | 14989 | Story | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-10-21 22:35
Sentimind | DPI-713 | 14983 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-15 22:04
Darkwatch | DPI-712 | 14982 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-15 22:04
ThreatPrism.culinda.com | DPI-711 | 14981 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-18 01:07
Background Process Updates | DPI-704 | 14964 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-13 05:30
UI development | DPI-703 | 14963 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-13 05:30
Design | DPI-702 | 14962 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ritika | 712020:2d9accdf-0317-4bb6-bb87-b5fb4b160527 | Shrashti Singhal | 2024-10-13 05:30
Surface Attack Scan - Loader Enhancement- RnD | DPI-701 | 14961 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-14 01:04
Add Addition of Scroll Bar. | DPI-673 | 14933 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Sneha Sonyabapu Guthe | 2024-10-10 04:11
More Info - Search Bar - Display "No Data Found" message when no results are returned. | DPI-672 | 14931 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Sneha Sonyabapu Guthe | 2024-10-18 03:18
Intel Vault - Rearrange the Column under the Export File. | DPI-670 | 14929 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Sneha Sonyabapu Guthe | 2024-10-18 03:15
Intel Vault - For the download the Export - Getting 504 Error Message. | DPI-669 | 14928 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Sneha Sonyabapu Guthe | 2024-10-18 03:14
HashGuard - Add PDF Download Option for Reports. | DPI-668 | 14927 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Sneha Sonyabapu Guthe | 2024-10-18 03:11
Intel Vault - Add Information Tooltip for IOC Value and Adversary Description to Avoid Truncation. | DPI-667 | 14926 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Sneha Sonyabapu Guthe | 2024-10-08 03:43
Intel Vault - Some of the IOC are still passing null value for the Status. | DPI-666 | 14925 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Sneha Sonyabapu Guthe | 2024-10-08 03:33
Intel Vault - Y-Axis Values Not Updating Dynamically: Current Count Exceeds Display Limit of 1000. | DPI-665 | 14924 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Sneha Sonyabapu Guthe | 2024-10-08 03:28
Intel Vault - - Adversaries Category Update Issue: Single Entity Update Modifies All Similar Entries. | DPI-664 | 14923 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Sneha Sonyabapu Guthe | 2024-10-08 03:31
Add keywords on SCan Darkeye along with DOmain | DPI-663 | 14922 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-10-01 00:48
News Feed - Key word search on news Feed- RnD | DPI-662 | 14921 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Shashwat Srivastava | 712020:bd17afcc-3aa8-42a7-be71-f016500a225e | Shrashti Singhal | 2024-10-30 02:05
Service to trigger email(sendgrid) to fixed TO address when DPI 659 executes on daily basis | DPI-660 | 14919 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 2024-10-09 02:47
Returned Adversary Names and IOC Values match the IOC already decimated or present in Intel Valut( not matched should be moved to intel Valut) | DPI-659 | 14918 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 2024-10-09 02:47
Matching of Adversary Names (Intel Valut with threat Prism) and returning the match with Adversary Names | DPI-658 | 14917 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Shrashti Singhal | 2024-10-09 02:47
Move IOCs from Threat Prism to Intel Valut | DPI-657 | 14916 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-09 02:51
UI for DPI 655 | DPI-656 | 14915 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 06:13
Bulk Search on IOC Value | DPI-655 | 14914 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-10-08 06:13
Service for DPI 621 UI | DPI-654 | 14913 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-10-08 03:56
Intel Vault- Incomplete data upload on Prime | DPI-651 | 14910 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Highest | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-01 07:43
Reports: Reports and UI mismatch- Tested on Prime Prod 25th Sep | DPI-650 | 14909 | Bug | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-13 04:19
Remove/Hide the navigation Page on SUper Admin | DPI-649 | 14908 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-18 04:47
Intel Valut Prime Data is visible to other clients | DPI-648 | 14907 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Highest | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-01 07:43
Integrations of services | DPI-645 | 14904 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Mahesh Katti | 2024-10-18 03:10
Sentry Issue- Call stack size exceeded for Intel Valut | DPI-644 | 14903 | Bug | Not Required/Duplicate | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-28 04:23
Sentry Issue in Prod for fetching Reputation score | DPI-643 | 14902 | Bug | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-14 01:54
Sentry Issue occurred when a associated domain is added to Darkeye Prod- Prime | DPI-642 | 14901 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-18 03:24
Sentry Issue- Invalid Resource Request- Production | DPI-641 | 14900 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-18 05:13
User/Client View Limitations | DPI-640 | 14899 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-10-08 09:12
Rewrite services to Create Intel Valut Tables | DPI-639 | 14898 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-10-08 09:12
Python Code to DB (using API) | DPI-636 | 14895 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-18 03:10
Intel Valut- Update doesn't update but append the value | DPI-630 | 14889 | Bug | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | High | Karan Pandey | 712020:1d22a1bc-2196-49a9-8eaa-f18940d51259 | Shrashti Singhal | 2024-10-01 07:43
Notification on Sent Email on UI- Pop up Box | DPI-627 | 14886 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 06:16
UI design sync with UI Development | DPI-626 | 14885 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-01 22:43
Reverse sorting on Date of Addition | DPI-625 | 14884 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-04 02:15
Re arrangements of Fields | DPI-624 | 14883 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 03:54
Re Direction to Threat Prism on Clicking on IOC Value | DPI-623 | 14882 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-10-22 00:58
Default TO Address of Email | DPI-622 | 14881 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-10-22 00:58
Email Sent date to be shown along with Decimated Status | DPI-621 | 14880 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 03:52
Adversary Category Drop Down- Edit IOCs | DPI-620 | 14879 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 03:49
Adversary Category Drop Down(fixed Values)- ADD IOCs | DPI-619 | 14878 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 03:47
UI facing collections list | DPI-600 | 14859 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rishav | 712020:a77a5f73-de04-4aad-8e6b-e8d31c7211c0 | Shrashti Singhal | 2024-10-08 03:08
UI facing tables list | DPI-599 | 14858 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rishav | 712020:a77a5f73-de04-4aad-8e6b-e8d31c7211c0 | Shrashti Singhal | 2024-10-08 03:08
Description of MYSQL Tables | DPI-598 | 14857 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rishav | 712020:a77a5f73-de04-4aad-8e6b-e8d31c7211c0 | Shrashti Singhal | 2024-10-08 03:08
Description of Mongo DB collection | DPI-597 | 14856 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rishav | 712020:a77a5f73-de04-4aad-8e6b-e8d31c7211c0 | Shrashti Singhal | 2024-10-08 03:08
Detailed list of SQL tables | DPI-594 | 14853 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-15 02:35
Collect Details on exiting mongo DB collections | DPI-591 | 14850 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-15 02:35
IOC once shared, shouldn't be able to share again | DPI-590 | 14849 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 03:46
Blockchain replacement of Third Party RnD | DPI-589 | 14848 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Shrashti Singhal | 60ba18cb66df7900708f9114 | Shrashti Singhal | 2024-10-08 10:55
UI development | DPI-585 | 14841 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-23 05:58
Side navigation - Enhancement | DPI-583 | 14839 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ritika | 712020:2d9accdf-0317-4bb6-bb87-b5fb4b160527 | Shrashti Singhal | 2024-10-22 22:57
Addition of handles- Sentimind- Enhancement | DPI-582 | 14838 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-18 03:17
Intel Vault Enhancements- More Features | DPI-578 | 14834 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-08 09:12
SuperAdmin- Navigate to different organizations- RnD | DPI-567 | 14823 | Task | To Do | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-08 10:55
UI Developement | DPI-564 | 14820 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-01 22:40
UI Design | DPI-563 | 14819 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Suyash Neware | 712020:fc1b6dae-6e3b-4f6c-a188-85d6cd8d4395 | Shrashti Singhal | 2024-10-18 04:50
Dashboard to monitor subscription- Services read from SQL, show to UI (get Request) | DPI-559 | 14815 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rishav | 712020:a77a5f73-de04-4aad-8e6b-e8d31c7211c0 | Shrashti Singhal | 2024-10-02 00:32
Darkeye- Super Admin- Email notifications on API keys expiry | DPI-554 | 14809 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | SaradhiMuneendra Gundabattina | 5da062fe8aaef20dc49834fc | Shrashti Singhal | 2024-10-18 04:50
Services | DPI-549 | 14804 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Rishav | 712020:a77a5f73-de04-4aad-8e6b-e8d31c7211c0 | Shrashti Singhal | 2024-10-18 05:14
UI design | DPI-548 | 14803 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Suyash Neware | 712020:fc1b6dae-6e3b-4f6c-a188-85d6cd8d4395 | Shrashti Singhal | 2024-10-18 03:10
UI development | DPI-547 | 14802 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-18 03:10
File Hashes research | DPI-541 | 14796 | Task | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Mahesh Katti | 5eccd1f2b1df560c071ff3b9 | Shrashti Singhal | 2024-10-18 03:11
Sentimind | DPI-531 | 14785 | Subtask | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium |  |  | Shrashti Singhal | 2024-10-21 22:34
CI CD for external Services | DPI-528 | 14782 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | gopal | 63b3b9f8b790087ed71179a2 | Shrashti Singhal | 2024-10-22 00:55
Integrate Prime IOC database- disseminated threats | DPI-408 | 14647 | Task | In Progress | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Varad Balasaheb Bhalsing | 641184c057f0c028e2f4ad8a | Shrashti Singhal | 2024-10-28 04:23
Threat Prism - Yara/Sigma Rules are Empty | DPI-402 | 14638 | Bug | Not Required/Duplicate | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Ajay Kumar Devarakonda | 5ee2157496beaa0aae1092f4 | Sneha Sonyabapu Guthe | 2024-10-28 04:23
User Benchmarking Darkeye | DPI-380 | 14616 | Story | Done | DPI | Darkeye Prod Issues | software | Shrashti Singhal | Medium | Naveen Adusumilli | 5f895e1253aaa400763096e7 | Shrashti Singhal | 2024-10-22 00:57