## Sprint Tasks
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Priority | Assignee | Creator | Date
Upload data to DB Tables | DPI-653 | 14912 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-30 04:57
Clean Client data and add new data | DPI-652 | 14911 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Shrashti Singhal | Shrashti Singhal | 2024-09-30 04:57
Once the APIs are achieved, It should stop sending emails | DPI-638 | 14897 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 00:52
API code snippet | DPI-637 | 14896 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Rohan Kaushik | Shrashti Singhal | 2024-09-24 01:14
Upload Files and Calculating Hashes- HashGaurd | DPI-635 | 14894 | Task | To Do | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-23 04:51
Reword Pop Up | DPI-634 | 14893 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-24 23:36
After uploading a file, if we attempt to upload another file, the information from the previous upload should be cleared. | DPI-633 | 14892 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 07:58
Export exactly same as table View( specially reverse sorting) | DPI-632 | 14891 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:06
When no IOC is selected, NO share or approve icon should be visible in Bulk Upload | DPI-631 | 14890 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:06
Info on Approved icon- This IOC is approved | DPI-629 | 14888 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:06
Reset Option On Charts View | DPI-628 | 14887 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:06
Reverse date sorting in Table View | DPI-618 | 14877 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:06
Risk Score drop down on Edit IOC | DPI-617 | 14876 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:05
Risk SCore drop down on Add new IOC | DPI-616 | 14875 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:05
Editing an IOC include Status, Risk SCore and Source | DPI-615 | 14874 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:06
Addition of Status, Sources, Risk Score to Add Row | DPI-614 | 14873 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:07
No editing of Analysts Name( Validation) | DPI-613 | 14872 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:07
Drop down for IOC Category Type | DPI-612 | 14871 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:05
Drop down for fixed values for Status | DPI-611 | 14870 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:05
Status is changed to Decimated when an email is sent | DPI-610 | 14869 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 05:05
Intel Valut Extended Functionality | DPI-609 | 14868 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 07:58
Email notification on third Party API keys/subscription expiry | DPI-608 | 14867 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-30 06:05
Database Tasks | DPI-607 | 14866 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-22 07:50
AI functionality | DPI-606 | 14865 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Somesh Fengade | Shrashti Singhal | 2024-09-22 07:49
UI development | DPI-604 | 14863 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-22 07:48
Services | DPI-603 | 14862 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-22 07:47
UI Development | DPI-602 | 14861 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-24 23:34
UI design | DPI-601 | 14860 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Suyash Neware | Shrashti Singhal | 2024-09-22 07:47
Deletion | DPI-596 | 14855 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-22 07:41
Review | DPI-595 | 14854 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Shrashti Singhal | Shrashti Singhal | 2024-09-22 07:41
Deletion | DPI-593 | 14852 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-22 07:40
Review | DPI-592 | 14851 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Shrashti Singhal | Shrashti Singhal | 2024-09-22 07:40
Enhancement Design | DPI-584 | 14840 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-19 08:45
Production Issue- Reverse NS Script- Variables used before assignment | DPI-581 | 14837 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-25 07:58
Review Infra Details | DPI-575 | 14831 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | V Thota | Shrashti Singhal | 2024-09-18 22:54
Upgrade/downgrade Infra | DPI-574 | 14830 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | gopal | Shrashti Singhal | 2024-09-18 22:53
Collect Metrics for Current Darkeye Infra- servers, ram, etc. and working capacity | DPI-573 | 14829 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Achyut Deshpande | Shrashti Singhal | 2024-09-18 22:53
Rewoke access | DPI-572 | 14828 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | gopal | Shrashti Singhal | 2024-09-18 22:52
Review User Access | DPI-571 | 14827 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | V Thota | Shrashti Singhal | 2024-09-18 22:52
Collect current User Acess | DPI-570 | 14826 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | C Sai Sampath | Shrashti Singhal | 2024-09-18 22:51
Threat Prism - Pagination is not showing .. | DPI-569 | 14825 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Sneha Sonyabapu Guthe | 2024-09-25 07:58
UI design | DPI-568 | 14824 | Subtask | To Do | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-12 00:52
Re run the code for all old data | DPI-566 | 14822 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 03:03
UI development | DPI-565 | 14821 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-23 22:55
Service to get full Social media records | DPI-562 | 14818 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Karan Pandey | Naveen Adusumilli | 2024-09-23 22:49
Sort not working on Domain Squatting for Self-Assessment. | DPI-561 | 14817 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Sneha Sonyabapu Guthe | 2024-09-25 07:58
Saving credit details- MYSQL DB | DPI-560 | 14816 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 00:52
Email triggers | DPI-558 | 14814 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 02:15
Check code for Credits and end date | DPI-557 | 14813 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 00:52
SBOM cors Issue- Threatrix API non functional | DPI-555 | 14810 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | gopal | Shrashti Singhal | 2024-09-30 09:42
Self & Vendor Assessment - All Domains - Add the Registrar Column. | DPI-552 | 14807 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Sneha Sonyabapu Guthe | 2024-09-25 07:58
Add scroll bar on Darkeye For the Navigation Menu | DPI-551 | 14806 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 07:58
Converting of Azure Functions to Microservices | DPI-550 | 14805 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-23 22:46
UI integration | DPI-546 | 14801 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 03:12
UI development | DPI-545 | 14800 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 03:12
Integrations of services | DPI-544 | 14799 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 03:02
UI development | DPI-543 | 14798 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 03:02
News Feed | DPI-542 | 14797 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-19 21:35
API Code snippet | DPI-540 | 14795 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Rohan Kaushik | Shrashti Singhal | 2024-09-25 03:02
Database cleaning | DPI-538 | 14792 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 03:12
Inserting client DB | DPI-537 | 14791 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 03:12
Design | DPI-536 | 14790 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-25 03:12
services | DPI-535 | 14789 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Karan Pandey | Shrashti Singhal | 2024-09-25 03:12
Database architecture planning | DPI-534 | 14788 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-25 03:12
Dark Watch | DPI-533 | 14787 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-19 21:35
Night Hauwk | DPI-532 | 14786 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-19 21:35
Scan Manager | DPI-530 | 14784 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-19 21:35
NAICS | DPI-529 | 14783 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-19 21:35
Re integration | DPI-526 | 14779 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-23 22:49
Development | DPI-525 | 14778 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-23 22:49
Design Changes | DPI-524 | 14777 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-23 22:49
IntelVault Database for Client Threats- Basic New Utility Development | DPI-523 | 14776 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-25 07:58
Integration | DPI-522 | 14775 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-25 03:11
Architecture | DPI-521 | 14774 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Somesh Fengade | Shrashti Singhal | 2024-09-25 03:11
FastAPI services | DPI-520 | 14773 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Jatin Singh | Shrashti Singhal | 2024-09-25 03:11
Database | DPI-519 | 14772 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Shashwat Srivastava | Shrashti Singhal | 2024-09-25 03:11
Threatprism.culinda.com session Management | DPI-518 | 14771 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Somesh Fengade | Shrashti Singhal | 2024-09-25 07:58
Design | DPI-514 | 14764 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-04 03:06
Design | DPI-513 | 14763 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-05 08:56
Inserting data in DB directly | DPI-512 | 14762 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Shrashti Singhal | Shrashti Singhal | 2024-09-05 08:56
Creation of new columns in DB(from services) | DPI-511 | 14761 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-05 08:56
Data for registration Date | DPI-510 | 14760 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-03 04:34
Data for registrar for all domains(whois) | DPI-509 | 14759 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-03 04:34
Change of Services for UI | DPI-508 | 14758 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-05 08:56
UI Development | DPI-507 | 14757 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:56
Standardizing Domain squatting in Self Assessment & vendor Assessment | DPI-506 | 14756 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:56
UI Design | DPI-505 | 14754 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Suyash Neware | Shrashti Singhal | 2024-09-23 22:55
Create Organization | DPI-500 | 14749 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-23 22:55
Darkeye Admin Portal- Onboarding org from UI | DPI-499 | 14748 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-25 07:58
Sentimind Addition of handles- Enhancement | DPI-498 | 14747 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-25 07:58
Integration of revised endpoints | DPI-497 | 14746 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-23 22:46
Python services to return last updated date of the feed | DPI-496 | 14745 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-23 22:46
Download Users from User Management | DPI-495 | 14744 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:54
Integration | DPI-494 | 14743 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:59
UI development | DPI-493 | 14742 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:59
Design | DPI-491 | 14740 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-05 08:59
Created Date/ Date of Registration | DPI-490 | 14739 | Subtask | Not Required/Duplicate | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-06 05:14
Scan date | DPI-489 | 14738 | Subtask | Not Required/Duplicate | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-06 05:14
Exception Handling of Login in case of Invalid user- Sentry Issue | DPI-487 | 14736 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:56
Exception Handling of Scan Manager- Sentry Issue | DPI-486 | 14735 | Bug | Not Required/Duplicate | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-02 00:07
Threat Prism - Export - Tags Data is missing (PROD Issue). | DPI-484 | 14733 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Sneha Sonyabapu Guthe | 2024-09-05 08:52
Dev Darkeye Login email sends url for prod- needs correction in email template | DPI-483 | 14732 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-05 08:51
Threats - DNS | DPI-482 | 14731 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Threats - Websites | DPI-481 | 14730 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Threats - Assets Inventory | DPI-480 | 14729 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
SSL List | DPI-479 | 14728 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
SOA Configuration Check | DPI-478 | 14727 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
NS Configuration Check | DPI-477 | 14726 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
MX Configuration Check | DPI-476 | 14725 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Real-Time Blackhole Check | DPI-475 | 14724 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Mail Servers Response | DPI-474 | 14723 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Name Servers Respond | DPI-473 | 14722 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Mail Server Reverse IP Addresses Match | DPI-472 | 14721 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Miscellaneous Vulnerabilities | DPI-471 | 14720 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Web Analysis - Config Check | DPI-470 | 14719 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Web Analysis - Pages Parsed | DPI-469 | 14718 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
WHOIS & DNS Name servers match | DPI-468 | 14717 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Domain Check | DPI-467 | 14716 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Assets config check | DPI-466 | 14715 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Open cloud storage | DPI-465 | 14714 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Open ports & services | DPI-464 | 14713 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | SaradhiMuneendra Gundabattina | 2024-09-05 09:04
Deployment Changes | DPI-460 | 14709 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | gopal | Shrashti Singhal | 2024-09-05 08:46
UI Changes | DPI-459 | 14708 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:46
Design for archiving and performing other actions | DPI-458 | 14707 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-05 08:45
UI Changes | DPI-457 | 14706 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 09:07
Service enhancing | DPI-456 | 14705 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-05 09:07
Need to design view for child node( for more number of nodes) | DPI-455 | 14704 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-05 09:06
Design for Indicating that the chart is clickable | DPI-454 | 14703 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-05 09:06
Breaches- Github Secrets | DPI-452 | 14701 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-05 09:04
Spelling correction of Registrar | DPI-448 | 14697 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:40
Redirecting source to a website- ThreatPrism | DPI-447 | 14696 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:49
Change of services | DPI-446 | 14695 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Karan Pandey | Shrashti Singhal | 2024-09-05 09:09
DB Change for self Assessment | DPI-445 | 14694 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Shrashti Singhal | Shrashti Singhal | 2024-09-05 09:08
Add mimecast tag in UI - self Assessment | DPI-444 | 14693 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 09:08
return a tag after entering domain to mimecast | DPI-443 | 14692 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-05 09:08
Services for achieving user | DPI-442 | 14691 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Karan Pandey | Shrashti Singhal | 2024-09-05 08:45
UI changes | DPI-441 | 14690 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:45
Archive User in DB | DPI-440 | 14689 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-05 08:45
Highlighting on Hovering on ThreatPrism | DPI-438 | 14687 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:48
If registrar name is not returned by API, let user fill it | DPI-436 | 14685 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:40
UI integration | DPI-435 | 14684 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:40
Run Whois here on domain name to fetch registrar automatically | DPI-434 | 14683 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-05 08:40
Search on Domain Squatting for Self-Assessment. | DPI-433 | 14682 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Sneha Sonyabapu Guthe | 2024-09-05 08:50
Allein Vault OTX Updater | DPI-432 | 14681 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-06 05:13
Malpedia Updater | DPI-431 | 14680 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-06 05:13
darkWatch- one service (place in prod env)prod, but individual DB management for dev, qa, prod | DPI-428 | 14677 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Somesh Fengade | Shrashti Singhal | 2024-09-05 08:46
AI Services Management - Darkwatch | DPI-427 | 14676 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Somesh Fengade | Shrashti Singhal | 2024-09-05 08:46
Archive User | DPI-426 | 14675 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:44
Sidebar collapse feature on all tabs | DPI-425 | 14674 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:33
Add button should be diabled | DPI-423 | 14672 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:41
Fill registrar yourself | DPI-422 | 14671 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:40
Cyber news in order of recent update | DPI-421 | 14670 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-25 07:58
Domain Squatting for self assessment- add mimecast tag | DPI-419 | 14668 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 09:08
Attack surface Visualization enhancement | DPI-418 | 14667 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 09:06
CSV download for more details | DPI-417 | 14666 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 09:04
Add new IOC types in adversaries | DPI-409 | 14648 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-05 08:59
Darkeye User Manual | DPI-393 | 14629 | Story | Done | DPI | Darkeye Prod Issues | software | Medium | Pranav Ramchandra Sarda | Shrashti Singhal | 2024-09-04 03:06
Updating IOC Parser Code for 2 sources | DPI-379 | 14615 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-06 05:13
Change Google Analytics Tag for Prod | DPI-364 | 14600 | Bug | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 09:13
Quality BenchMarking DarkEye | DPI-363 | 14599 | Story | Done | DPI | Darkeye Prod Issues | software | Medium | Sneha Sonyabapu Guthe | Shrashti Singhal | 2024-09-25 07:58
Job Scheduler python code | DPI-357 | 14593 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 03:02
Job Scheduler on CM variants | DPI-356 | 14592 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Rishav | Shrashti Singhal | 2024-09-25 03:02
Microservices | DPI-355 | 14591 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Rishav | Shrashti Singhal | 2024-09-25 03:02
Design development | DPI-354 | 14590 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ritika | Shrashti Singhal | 2024-09-25 03:02
Create DB to store Data fetch from API | DPI-353 | 14589 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Varad Balasaheb Bhalsing | Shrashti Singhal | 2024-09-25 03:02
Criminal IP API tech stack addition to scan | DPI-352 | 14588 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Karan Pandey | Shrashti Singhal | 2024-09-25 07:58
Functionality Building | DPI-329 | 14542 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Medium | Somesh Fengade | Shrashti Singhal | 2024-09-22 07:42
UI Development | DPI-328 | 14541 | Subtask | In Progress | DPI | Darkeye Prod Issues | software | Medium | Mahesh Katti | Shrashti Singhal | 2024-09-22 07:42
Filter Integration on UI | DPI-247 | 14421 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:30
Java Service on Scan Status | DPI-246 | 14420 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-05 08:30
Filter integration on UI | DPI-245 | 14419 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:29
Java Services for Filter | DPI-244 | 14418 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-05 08:29
UI filter enable/Integration | DPI-243 | 14417 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:29
Java services for Filter on pagination | DPI-242 | 14416 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-05 08:29
Integrate the end points- if required to show In progress | DPI-236 | 14410 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | SaradhiMuneendra Gundabattina | Shrashti Singhal | 2024-09-05 08:30
Implement a In Progress Scan status in Services | DPI-235 | 14409 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Amitabh Sharma | Shrashti Singhal | 2024-09-05 08:30
Add a third scan Status- IN PROGRESS | DPI-234 | 14408 | Subtask | Done | DPI | Darkeye Prod Issues | software | Medium | Ajay Kumar Devarakonda | Shrashti Singhal | 2024-09-05 08:30
Progress status, when scan is in progress | DPI-230 | 14404 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-05 08:30
Filter on Vendor Risk Rating- Vendor Assessment | DPI-229 | 14403 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-05 08:28
Filter on Reputation Score- Vendor Assessment | DPI-228 | 14402 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-05 08:29
Filter on Scanned Status- Vendor Assessment | DPI-227 | 14401 | Task | Done | DPI | Darkeye Prod Issues | software | Medium | Naveen Adusumilli | Shrashti Singhal | 2024-09-05 08:29
Intel Valut- Swimlane Integrations- Mimecast, Logrtyhm, Trellix- Ticket to be updated after Client Discussion | DPI-99 | 14271 | Task | To Do | DPI | Darkeye Prod Issues | software | Medium |  | Shrashti Singhal | 2024-09-23 05:02